## Improvements
Elements/Components | Improvements | Priority | Screenshots/videorec/Design URLs | Capanicus comments | MCM Comments
UI Designs: | Also need to make the UI well-responsive for mobile/tablet view. | High
| Home Dashboard, Chat/Inbox, Phone Dialer, Phone Section, Video Meetings, Side Menus, Departments, Admin Section: DID purchase(Sign up), IVR(Text to speech), AI tools UI updates and improvement.png | High
AI Feature: | AI assist in chat dashboard. | High
| Need to create our own AI model with Ollama | High
| AI writer - The chat functions should include chat AI assist for user's quick texting of last question | High
| AI Call Tags - Auto-categorizes calls (e.g., "Billing," "Support") for reporting. | High
| AutoTransfer to real agent in ChatBot. | High
| AI agents sentiment dashboard. | High
| Chat Admin can barge between human agent and customer. | High
| Click to dial on Domain Chatbot widget, in the chat call will transfer active agent | High
| AI receiptionist with scheduled callbacks: should be able book an appointment if the human agent is not available at that time. | High
| Chatbot appearance and Agent test button on domain. | High
| OutBound AI Reception | High
Chat: | Need to add all chats filter which will show overall chats including omnichannel chats with their respected logo/icons, as given in design reference | High
| The user should be able to see Message not Delivered, Delivered and Seen ticks. | High
| A member cannot ping/tag other members on team chat (for example, @admin). | High
| In chat, attachment/Image/Video should be visible in small window. | High
| In chats, add the search bar option for searching the previous chats. | High
| In the chat section there are no specific options to pin a direct chat or group chat(max should be 3 chats). | High
| If I want to select and forward multiple messages (3–4) at a time, there is no option available to do so, similar to WhatsApp. | High
| Add a “Jump to Latest Message” button(perhaps an icon: DownArrow) in the chat. When the user scrolls away from the bottom, the button appears and allows direct navigation to the most recent message without manual scrolling, similar to WhatsApp. | High |  |  | shailendra - fixed
| In the chat section, features such as contact sharing, polling, audio messages, and event options—similar to WhatsApp—are not available. | High
| In the Notes/folders view, the creator’s name and creation time should be displayed below or beside each created note/folder title. | High
| Creation messages show the creator and note/folder name, but deletion messages only show who deleted it, not the name of the deleted note or folder. | High
| If the chat is deleted by any user, there should be a notification of the deleted chat instead of the original one(referenced by whatsapp). | High
High
Multi-Domain Environment | We will implement a Multi-Domain Environment that enables the creation of separate domains for each company, such as AcePeak, MCM, and others. Each domain will function independently with its own dedicated email configuration, omnichannel setup, merchant gateway integration, CRM system, and AI tool API keys. Additionally, every domain will have the ability to customise its logo, profile settings, and minor UI colour elements to maintain brand identity. This structure ensures complete operational separation, secure configuration management, and independent control for each business entity within the platform. | High
Omnichannel Chat Integration: | MS Teams and Viber | High
| WhatsApp contacts, user/admin shall be able to send messages via contacts section/search contacts on WhatsApp omnichannel | High |  |  | Anusha-Fixed
Phone: | The Recordings storage will be truncated after 7 days(if the add on plan is not bought). | High
| The Call Records Call history UI should have a back button to redirect on dialer. Reference UI design: CallHistoryUIBack-Improvement.png | High |  |  | Anusha-Fixed
| There should be an auto call transcript option to the agent, manager or admin. | High
| Call Recordings deletion function for admin(and those users which admin is given access to). | High
| After Call feedback IVR Function shall be there to test. | High
Reports: | Campaign Log Reports - Historical record of all Campaign Calls for tracking. | High
| DID Log Reports - Historical record of types of DID numbers for basic tracking for Admin/Super-Admin. | High
High
Analytics: | Adoption Analytics - Track how features are being used by the team to ensure ROI. | High
| Business Analytics Pro: Advanced, customizable reports and deeper insights into trends. | High
High
High
Home: | Chat summary on Home dashboard | High
| The MCM brand logo should be replaced with the new one. | High
| A search Bar should be on top of the UI, where the user can search required functions (as per the figma design) | High
Auto Dialer (Agentless): | Eliminates agent interference and enables dialing via AI agents to maximize outbound productivity just like vapi. | High
Video: | Add a "Join" button in the notification section to directly join a meeting when invited. | High
| Add a ‘End Meeting’ button on this page to allow closing the meeting without opening it. End meeting button on ongoing meeting.png | High
DID Numbers: | 1. when the DID is released, that DID shall be released on next billing(so the user can revert the release before the billing). | High
| 2. DID purchase design structure should be better. | High
Department: | 1) Department extension number should be clearly visible alongside each department entry. | High
| 2) Department member count indicator should use a neutral/primary color (e.g., blue) instead of red. | High
| 3) The department manager name should appear directly below the department name to reflect hierarchy. as "Manager – <Name>" | High
| Attachment: UI updates and improvement.png | High
| 4) add in the Users search bar Placeholder: “ Search by name or extension number ” | High
| Also in the Department tab search bar Placeholder: “ Search by name and extension number “ | High
High
CRM Integration- | Salesforce HubSpot Zoho CRM Microsoft Dynamics 365 Zendesk (Zendesk Sell) Pipedrive Freshsales (by Freshworks) Monday Sales CRM Copper CRM SugarCRM Insightly Oracle NetSuite | High
Plan: | Need to create plans for Europian countries. | High
| Need to create plans for rest of other countries. | High
Inbox: | Add search functionality in Message Inbox to find contacts by name or number | High
| MMS And Fax | High
CNAM (Caller Name Display): | Displays your company name on outbound calls to increase answer rates. | High
911 and other numbers Emergency Calling: | Mandates ability to connect to emergency services (Compliance), which needs an actual company address. Reference: https://en.wikipedia.org/wiki/List_of_emergency_telephone_numbers#:~:text=In%20many%20countries%2C%20dialing%20either,180 | High
Visual Call Flow/Work Flow Designer: | Drag-and-drop interface to easily configure how calls are routed (IVR). | High
Cost Center Management: | Track usage and allocate costs to specific departments. | High
Call Duration Limits: | Force disconnect calls after X minutes (useful for sales/support limits). | High
addon purchase Billing
Core Telephony & Call Handling
0 | Description
SIP Trunking – Auto Device Provisioning | Automatically configures SIP phones (Cisco, Yealink, Polycom, etc.) without manual credential setup, simplifying deployment.
SIP Trunking – Multi-Vendor Auto Provisioning | Enables zero-touch provisioning for multiple SIP-compatible devices across locations.
Call Routing Logic (Advanced Engine) | Intelligent rule-based routing based on caller ID, time, IVR input, agent availability, and queue status.
Dynamic Routing | Real-time routing adjustments based on queue length, agent load, or live performance metrics.
Skill-Based Routing (Basic Model) | Routes calls to agents based on defined skill tags.
Advanced ACD Framework | Full Automatic Call Distribution system managing high-volume inbound calls with intelligent logic.
Priority-Based Routing | Allows VIP or urgent callers to be prioritised in queues.
Data-Driven Routing (CRM Based) | Routes calls using CRM/customer history data.
IVR + ACD Integration | IVR collects caller input and feeds routing engine for intelligent distribution.
Estimated Wait Time | Announces live wait time and queue position.
Callback in Queue | Offers caller a callback option instead of waiting on hold.
Real-Time Queue Monitoring | Live supervisor view of queue metrics and agent states.
ACD Reporting & Analytics | Historical queue performance, SLA tracking, abandonment rate analysis.
Specific Routing & Omnichannel
Feature | Description
Omnichannel ACD | Unified routing across voice, chat, email, and social channels.
AI-Based Routing | AI-Based Routing is a smart call routing method that uses artificial intelligence to decide which agent should handle a customer interaction. Instead of simply sending calls based on fixed rules like “longest idle” or “round robin,” the system looks at historical data such as past customer interactions, agent performance, resolution rates, customer satisfaction scores, and even sentiment. It then predicts which available agent is most likely to achieve the best outcome for that specific customer and routes the call accordingly.
Skills-Based Interaction Routing | Multi-channel routing based on agent skill mapping.
Attribute-Based Routing | Advanced routing using attributes like region, certification, or language.
Channel-Based Flows | Separate routing workflows per communication channel.
Visual Flow Designer | Drag-and-drop UI to design routing and IVR workflows.
Concurrency Limits | Controls number of simultaneous chats/emails per agent.
ACW Cancellation | Allows wrap-up state override for urgent interactions.
Omnichannel Auto/Manual Assignment | System assigns automatically or supervisor manually assigns interactions.
Digital Channel Integrations (Telegram, Viber, Lime, Twitter, LinkedIn, MS Teams) | Integration with major messaging and social platforms for unified routing.
Messaging & Collaboration
Feature | Description
Task Creation in Chat | Allows agents to assign and track tasks within chat conversations.
Unified Inbox | Single interface for SMS, voicemail, fax, and digital messages.
Video Conferencing
Feature | Description
Video Conferencing Integration | Native or integrated video meetings for customer or internal collaboration.
Large Meeting (1500 Participants) | Webinar-scale meeting capability with high participant capacity.
Whiteboarding | Shared collaborative drawing canvas in meetings.
Annotation | Draw/highlight on shared screen during meeting.
Save Whiteboards/Notes | Persistent storage of meeting collaboration content.
Live Translation | Real-time caption translation in multiple languages.
AI & Automation
Feature | Description
FlowBuilder | Visual builder for IVR and routing workflows.
FlowBuilder Templates | Industry-specific workflow templates.
AI Agent / IVA (Voice & Chat) | Conversational AI for automated customer support and call deflection.
Chat Real-Time Translation | Live AI translation of chat messages.
Auto Dialer Script Approval | Admin approval workflow for outbound scripts.
Auto-Scoring (Calls) | AI evaluates calls using predefined QA criteria.
Supervisor Assist (AI Alerts) | AI alerts supervisors about negative sentiment or compliance risk.
Generative AI Message Writer | AI drafts email/chat responses.
Grammar & Tone Assistant | AI suggests corrections and empathetic tone improvements.
AI in Analytics | Predictive workload forecasting and anomaly detection.
Real-Time Agent Assist | AI provides live suggestions during interactions.
AI Knowledge Base Search | AI surfaces relevant help articles automatically.
Real-Time Coaching (AI) | AI nudges agents during calls (empathy prompts, compliance reminders).
AI-Powered CSAT & Conversation Intelligence
Feature | Description
AI-Powered CSAT | Predictive CSAT scoring using sentiment, keyword, and behavioral analysis.
Emotion Detection | Identifies anger, frustration, joy, confusion.
Context Sensitivity (NLP) | Detects sarcasm, tone changes, contextual meaning.
Sentiment Scoring | Assigns numeric sentiment value to interactions.
Conversation Intelligence | Analyzes themes, resolution success, and agent performance impact.
Predictive CSAT Model | Generates CSAT for 100% interactions without surveys.
AI Scorecards | Automated QA scoring against predefined compliance & performance metrics.
Supervisor & Agent Experience
Feature | Description
Call Monitoring Groups | Configurable supervisor-to-agent monitoring permissions.
Screen Monitoring | Supervisors view agent desktop in real-time.
Real-Time Supervisor Dashboard | Live queue and agent performance view.
Call Reshuffle | Supervisors manually reassign queued calls.
Silent Monitoring with Analytics | AI-triggered alerts for long wait or negative sentiment calls.
Agent Scorecards | Performance dashboard for individual agents.
Leaderboards | Gamified ranking system based on KPIs.
Last Call History Context | Displays prior interaction context automatically.
System Administration & Management
Feature | Description
SCIM API Integration | Automated HR-based user provisioning and de-provisioning.
Bulk Provisioning Tools | CSV or mass import user creation.
SSO | Corporate login integration (SAML/OAuth).
Multi-Site Management | Partitioned management across business units/sites.
Divisions | Organizational segmentation for large enterprises.
Partitioned Phone Books | Restricted internal directory visibility by division.
Reporting & Analytics
Feature | Description
Real-Time Dashboards | Live queue, SLA, and agent performance metrics.
Wallboards | Large-screen configurable KPI display.
Real-Time Data API | External access to live system metrics.
Historical Reporting | Past performance trend analysis.
Standard Reports | Prebuilt KPI reports (AHT, SLA, Abandon Rate).
Custom Reports | User-defined reporting with filters and metrics.
BI Integration | Embedded or export to business intelligence tools.
Custom Analytics Export | Raw data export and API integration.
Security & Reliability
Feature | Description
High Availability (99.999%) | Redundant infrastructure ensuring minimal downtime.
Geo-Distributed Data Centers | Multi-region deployment for resilience.
Load Balancing & Failover | Automatic traffic rerouting during failure.
Disaster Recovery Plan | Backup and recovery framework with DR drills.
Encryption (TLS, SRTP, HTTPS) | Encrypts signalling and media in transit.
Encryption at Rest (AES-256) | Secures stored recordings and data.
MFA | Multi-factor authentication for enhanced login security.
Fraud Monitoring | Detects abnormal call patterns and toll fraud.
IP Access Control | Restricts platform access by IP range.
Audit Logs | Tracks admin actions and system changes.
GDPR/Compliance Controls | Data privacy compliance and deletion tools.
DLP & Data Masking | Detects and masks sensitive data in transcripts.
Call Quality Monitoring | QoS metrics and call health tracking.
Public Status Dashboard | Public uptime and system health page.

## IssuesBugs
No. | Elements/Components | Issues | Screenshots/videorec URLs | Capanicus comments | MCM Comments
Web
A. Phone
Fixed
6 | Profile-> incoming calls -> Forward Calls | Play Announcement is not working in User Profile of Phone tab. |  | FIXED | Fixed
17 | Call Dialer | Need to implement Phone Number Format with Country Code: +1 (555) 123-4567 |  | FIXED | Fixed
3 | Call Merge | The MasterCaller stucks at call when all other recipiants are left. |  | couldnt reproduced | Fixed
Pending
1 | call transfer to extension | When a call is made from the UCaaS web to a non-UCaaS number and then transferred to another UCaaS extension, the call connects successfully. Charges are deducted for the first user’s call log and charges are correct, but charges for the second user (extension transferred call recipient) are not shown in the call-log report. |  | Pending | Pending
2 | transfer call report on external number | When the user transfers the call to an external number, the call duration and cost is not being considered on the master caller's call report. |  | Pending | Pending
4 | Dialer search bar | The user should be able to search saved contacts on the dialer, including users with their extension and contact number(which is added in user details). |  | Improvement | Pending
5 | Recordings Charge | Need to implement call recordings charge on companies user base capping, and storage should be allotted differently |  | In Progress | Pending
7 | Sentiment Analysis | The Sentiment analysis is not working as expected. |  | Need to Discuss | Pending
8 | Voicemail Timeout issue | The voicemail stays longer than 30 seconds. |  | As discussed with tauseef Sir there is no logic to end the voicemail after 30 sec even the caller is leaving the message.. but it happens when no one speaks for 3 to 4 sec it will be disconected | Pending
9 | Decline with message | On Inbound calls, Decline with message is not working, SMS cost prompt and DLC required(if needed) restriction shall be shown to the user. |  | FIXED | Pending
10 | Free Call Minutes | Call charges are being deducted even after the free call minutes are finished. |  | Testing | Pending
11 | Call Recording Deletion | if the recording storage is free, we'll delete all recordings after 7 days after notifying the user before certain time. |  | Confirmation pending from furkan sir | Pending
12 | transfer calls | when the user does an extension call and then the same caller transfers the extension call to another extension, all calls will be disconnected immediately. |  |  | Pending
13 | monitoring | In the Monitoring section, most features are not functioning correctly. Only Listen and Barge are available, and within Barge, functions like Mute, Transcripts, Hold, and others don’t work. The Campaign section shows no reports, and even when a campaign is opened, it still displays Monitoring – Call Queue at the top. Overall, the sections are not working properly. |  |  | Pending
14 | Transcription | System does not keep transcription on when user close the Call UI and get back to transcription. |  | FIXED | Pending
15 | Transcription in Hindi | Transcription in Hindi is not working now |  | Saurabh Please provide Azure details | Pending
16 | Call Monitoring | Except All Calls, All other call monitoring tabs are not working, also call queue waiting callers records are being stuck on tab |  |  | Pending
18 | call recoring on in-coming call | On incoming calls, call recording starts automatically even when the call recording setting is disabled. |  |  | Pending
B. Chat
Fixed
29 | Chat > adding notes | Formatting option labels are visible for a few milliseconds before the notes editor loads properly. | UI flicker in notes.webm IMAGE: UI notes lable name shows while it is loading .png |  | fixed
16 | Chat Delete access | If the user does not have access to delete, the user still can delete chats via team, favorites and direct tab | detele all chat.mp4 | FIXED | fixed
17 | Chat Reload Issue | sometimes the user cannot see previous messages and even previous does not reload automatically until the user refreshes the page |  | FIXED | fixed
18 | Chat Reload and Jump to Bottom | To stabilize the feed, implement a top-loading spinner combined with CSS overflow-anchor: auto to prevent the view from jumping when older messages prepend. Additionally, add a floating "down-arrow" button that appears when the user scrolls up, providing a one-click shortcut to return to the latest message. | https://capanicus.slack.com/files/U09S8RH17J5/F0AAKHXP71Q/chatloadingandjumptobottom.png | FIXED | fixed
19 | Click on Created folder | If the user clicks on created chat folder name via vague notification, then gets back on chat, the user will be redirected to the top of the chat. |  | FIXED | fixed
20 | Chat> Click on Replied Message | Sometimes, when clicking on a reply message, it does not redirect to original message and instead shows the notification: ‘Original message not found. It might be in an older conversation.’ |  | FIXED | fixed
23 | chat->folder | There is no character limit on note and folder names. |  | FIXED | fixed
25 | Join Call Button | Join button which was removed, is still pending to connect ongoing team chat call. |  | FIXED | fixed
28 | Chat | While editing a message draft in one chat, switching to a different chat carries the same edited draft into the other chat. When the draft is sent, it is delivered to the original chat instead of the currently active chat. | recording.webm | FIXED | fixed
30 | Chat > NOTES | Deleted note activity redirects to notes instead of showing deleted state. Also group or team does not shows as it is whether the team name is in UPPERCASE or lowecase style | Team or group Name does not shows as it is written uppercase and lowecase and second notes after deletion, edited.mp4 | FIXED | fixed
31 | Team Chat> removed/left user | In a team group, if any user is removed or leaves the group, their name and profile avatar are not shown in their previous chat messages. | Removed/left user chat message issue.mp4 | FIXED | fixed
32 | Reply chat | When replying to a message in one user’s chat and then opening another user’s chat, the typed reply message appears in the other user’s chat. | Reply message issue.mp4 | FIXED | fixed
| In Team Delete message | In Team group if any user delete chat message name of the user is not showing, who is deleted the message is not showing. | delete message chat UI.png
Pending
21 | Chat>message | When typing a long message in the chat input field, pressing Shift + Ctrl to move to a new line instead moves the cursor directly to the bottom line. |  | In Progress | pending
| Team Chat> Deleted user | If a user is deleted, their name and profile avatar are not shown in their previous chat messages in the team group. | Deleted user profile name avatar issue.mp4 |  | pending
24 | Chat AI Assistant | A chat AI assistant shall be included for user's quick & easy issue resolution as per the FIgma design given in "Screenshots/videorec URLs" column |  | Please provide video or Screenshot | pending
26 | Chat Section | A member cannot ping/tag other members on team chat (for example, @admin) |  | In Progress | pending
27 | chat | the change group photo not available after creating a group. |  | In Progress | pending
22 | chat->emoji | There are some categories of emojis are missing, e.g., flags, |  | In Progress | pending
| Chat list | chat pic profile |  | NEED TO DISCUSS | pending
C. Video Meeting
Fixed
33 | Join Meeting Via Link | If an unknown user joins the meeting via the URL link and enters only spaces in the Name field, the user is still able to join the meeting. |  | FIXED | Fixed
Pending
| recording | In the video meeting, when I click the recording button, a popup appears saying 'Recording stopped |  |  | pending
34 | video - recording | When I click the recording icon during a meeting, it loads and starts recording, but the recording info—like how long it has been recording—doesn’t show. |  | FIXED | pending
35 | Video Improvement Part | Suppose I scheduled a meeting for one hour later and switch to another tab to work. When the meeting time arrives, I should receive a system notification. However, no system notification is received. |  | FIXED | pending
36 | join buttton in notification secction | Add a "Join" button in the notification section to directly join a meeting when invited. |  | FIXED | pending
37 | join meeting multiple time | A user can join the same meeting multiple times from different tabs using the same ID and name, which is not expected behavior and should be fixed. 1. There is no user validation on checking if the user is already on a video call. | recording.webm | FIXED/ Lets Discuss this on call. | pending
E. Home
40 | Campaign Dashboard | In the campaign dashboard, the agent report displays the wrong count of campaigns assigned to agents. |  | Please add video Couldn't reproduced | pending
F. User Settings
41 | Settings - Video | When we set profile photo from android, on the web version, the user won't be able to remove that profile photo |  | FIXED | Fixed
G. Admin Section
42 | Call Queues Creation | The custom made user role can't be the manager of a Call Queues, despite giving all permissions to that user role |  | discussed with raman | pending
43 | admin - sms/calling rates | In Admin Settings → SMS/Calling Rates, only Outbound Rates are shown, without clearly indicating whether they are for SMS or calling. After selecting a country, landline and mobile rates appear, but SMS or calling is still not specified. Also, searching for Canada shows two landline rates. |  | FIXED | pending
44 | IVR Function | The overall IVR UI is not user friendly and does not seem professional and has some Logical bugs, the media function development is not completely implemented, where the user should have features to make the text to speech audio in multiple voices and accents, sample designs are given in "Screenshots/videorec URLs" column | Sample image 1.jpeg Sample image 2.jpeg | Improvement | pending
45 | IVR Function | The Generic Key press function does not work on IVR calls, such as if the IVR is set on pressing * to go back on previous menu and # to repeat the present menu, also there is not option for 0 digit keypress | IVR Previous and Repeat Manue.mp4 | pending | pending
46 | User ID | multiple systems with a single user ID can call different users without knowing each other. |  | Discuss tauseef Sir | pending
I. Campaign
Fixed
49 | Campaigns Reports | In some campaigns the notes are visible even when the call is getted cut |  | FIXED | Fixed
Pending
47 | Dialed Numbers | After running the campaigns the connected calls number is not visible |  | (Working fine with not anwered), Unable to check answered (webhook issue) TESTING | pending
48 | Campaign >Campain Logs | In campaign call reports, the Notes option appears for certain calls even when the call status is Cancelled. |  | FIXED/ Please check this | pending
50 | Create Campaign | While creating a campaign in media before submitting the campaign settings when the user changes the dialer the script is removed from it and during the campaign calls the script is empty. | campaign script.webm | Not an issue : We kept type in Script based on the dialer : When dialer is changed the Script will also should be selected as per dialer chosen. | pending
51 | Campaign>Recording | When an agent does not have recording access at the agent level, call recording does not work during a campaign, even if recording is enabled in the campaign settings. | Campaign Call recording issue.mp4 | Discussed with Adnan.. | pending
I) Inbox
Fixed
57 | SMS -> Message | In the Inbox, when I try to send a message to any number, a “"available_balance" is not allowed” pop-up appears, and the SMS is not sent. |  | Add video | Fixed
53 | SMS -> Message | When the sms is sent from report a popup occurs no sufficient balance to send message but by clicking in confirm the message is sent |  | FIXED | Fixed
81 | Sms > Plans > Free SMS | Free SMS are not being deducted from given free SMS in plan -> Billing. |  |  | Fixed
54 | Inbox > SMS | Contact profile picture is not displayed in Inbox conversation list or contacts | Contact profile picture issue.mp4 | FIXED/ Please check again working fine | Fixed
Pending
70 | SMS-Search bar | names wth numbers saved in contacts and numbers used on which SMS are sent shall be visible on the search bar including users with their contact number(which is added in user details).. |  | Discuss | pending
55 | Inbox > SMS Tab | Add search functionality in Message Inbox to find contacts by name or number |  |  | Pending
56 | SMS -> Message | Delivery Status Missing: The system does not notify if the SMS is sent, delivered, or failed.UCAAS |  | FIXED | Pending
J) Contacts
81 | Contacts and Search bar | Users shall be added with their contact numbers and other info (which is added in user details). |  |  | Pending
| update same contact issue | If a new contact is created for the first time in any company and the same contact is later created in another company, when the contact is updated, the username of the user who created it in the first company is shown on the updated contact. | contact Update issue.mp4 |  | Pending
K) DID Numbers
Fixed
|  | Added inventory numbers shall have their available features(sms/calls in/out) |  | FIXED | Fixed
Pending
|  | While purchasing the DID, user shall see those features before billing parts. |  |  | Pending
58 | Billing -> Plan | Billing → Plan → DID(s) tab, the cost of purchased DIDs is not displayed. | DID cost.mp4 | FIXED | Pending
| Add User -> assign number | if creating bulk users(e.g more then 2 or 3 ) and assigning their DID numbers using the ‘Assign Now’ option after payment, the same DID is being added two-three times. | Same DID Assign two to three time.mp4 |  | Pending
| Add/Assign Same DID Number issue | Users from different companies are able to purchase and assign the same DID numbers at the same. | Assign and purchesing same did issue.mp4 |  | Pending
M) Others
Fixed
65 | Error 404 | Sometimes the Error 404 occurs on some accounts, on which upon clicking "Go To Homepage", The button does not redirect and refresh up on homepage | ClickOnHomepageRedirectionErr404.mp4 | FIXED | Fixed
66 | Account Renewal | all users except admin, are able to login and use all functions(excluding billing related). |  |  | Fixed
60 | Knowledge base DB Collision | some companies are having the same knowledge bases created on a single company, this means all knowledge base records are being unified in several companies: |  | FIXED | Fixed
61 | Login OTP | There should be an OTP attempt limit, for example: if the user is not able to insert otp correctly for 5 times |  | FIXED | Fixed
62 | Login OTP | There is no otp expiration rule, such as after 10-15 mins the otp shall expire. |  | FIXED | Fixed
Pending
| Deleted user visibility | Deleted users must not be visible in any actions, such as i) While starting a new chat or creating/editing team chat, deleted users still exists in group chat members list. ii) Users/Inventory/departments lists iii) Licence management list iv) DID inventory list(assigned DID will be un-assigned) v) IVR/Call Queues/any Forward to extension actions. vi) Any search bars, if it includes a separate users list. | Deleted_Users_still_exists_in_group_members_list.mp4 | FIXED | Pending
59 | Password Reset Link Has No Expiration Time v1.2.8 | There is no time limit or expiration for the password reset link, as it remains valid regardless of when it is opened, though once used password reset link, will be expired when the user uses on second time, but it should notify as expired at initial screen after trying to use it second time. |  | FIXED/ Please explain which Scenario u are reffering to is not fixed or add video | Pending
63 | User owned DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin |  | Improvement | Pending
64 | Overall UI responsiveness | When the user/admin does any change for another user, such as changing their role, creating a department or team chat and adding a scheduling and inviting other users/members, etc. The bug is that the application is not implementing real-time data updates and relies on manual page refreshes, which is an issue with frontend or backend communication, possibly a missing or improperly configured WebSocket connection, incorrect event handling, or issues with a live-reloading development server. The UI needs a mechanism like WebSockets or AJAX calls to listen for server-sent events and update the display dynamically, rather than waiting for the user to manually refresh |  | FIXED | Pending
Android
A) Home
Fixed
2 | Home -> Admin controls | Call forwarding is not functioning. If we set any value (such as forwarding to an external number) and click Save Changes, the values are not saved. Also on UI, the user is able to forward calls on its own extension. |  | FIXED | Fixed
4 | Home | There is currently no option in the UCaaS application to view the account balance. |  | FIXED | Fixed
Pending
1 | Home>Dashboard | In the Home Dashboard, the Outgoing graph is incorrectly including incoming ,voicemail, missed calls counts. |  | In Progress | Pending
3 | voicemail setting | Voicemail is not working. Even after enabling voicemail and setting an email address, the calls are not being forwarded to voicemail. Also the connect to voicemail does not work or unclarified. |  | Pending | Pending
5 | Profile | First, there is no option in the application to delete the profile picture, and there are synchronization issues between the web and the application. While the profile picture syncs correctly when uploaded, deleting it requires logging out and then logging back into the application for the change to take effect. Also the user cannot remove that profile photo from web app. and upon Logging into others account, the same profile photo will be set on android app. |  | FIXED | Pending
B) Phone
Fixed
6 | Home>Extension Calls | During extension calls, when the user clicks on the transfer option, a number search bar appears. Currently, typing any number in this bar can transfer the call to an external number. However, the transfer feature should only allow searching for and selecting extension numbers or user names within the system, |  | FIXED | Fixed
9 | Dialer | There should be a proper flow for outbound calls, including connecting, calling, and ringing. |  | FIXED | Fixed
10 | Dialer | The caller’s phone is ringing, but the agent’s phone still shows “calling". |  | FIXED | Fixed
Pending
7 | Phone calls | During a DID call, when clicking on the Transfer option, there is no option available to transfer or speak the call to an external number. |  | Testing | Pending
11 | Dialer | if call Recipient declines the extension call but it keeps ringing on the caller side until the ring timeout ends, and then it stops. |  | It happens due to multiple logins | Pending
12 | Home > User | During extension calls, the call disconnects for both parties when transferring the call. |  |  | Pending
| Transfer Call | When a user makes an extension call and then transfers that call to another extension, all calls get disconnected immediately. |  | Testing | Pending
8 | Phone calls > Filter | In the phone call section, the filter options are not working as follows: This Week Last 7 Days This Month Last 30 Days Last Month |  | Already working Fine | Pending
C) Inbox
Fixed
14 | inbox | The search functionality does not Exist. |  | FIXED | Fixed
D) Video
Fixed
18 | Invite Members | In Invite Members, once members are selected and you navigate away and return, the selected members are not shown as checked, even though they are still selected. |  | Done | Fixed
16 | Past Meetings | In past meetings, clicking on attendees does not show the user information. |  | FIXED | Fixed
17 | Feedback | The feedback option does not exist |  | FIXED | Fixed
19 | Video Meeting | When starting a recording, a popup appears saying "Failed to start," but the recording actually begins after clicking OK. Similarly, when stopping the recording, a popup shows "Participant left." |  | FIXED | Fixed
21 | Video Meeting | If a meeting is scheduled with a password, all meeting details are shown later, but the set password is not displayed. |  | FIXED | Fixed
22 | Video Meeting | In the video call section the features are missing: 1. Recording 2. Screen Sharing 3. Reaction options 4. Chat feature 5. Info option (with share invite link) 6. Participants and host accesses 7. Background effects 8. Presentation mode 9. invite other users via email | video call missing feature .mp4 | 1.Chat Feature Done 2.Reaction option Done 3.Info(Invite) option Done 4.Participants Done 5.Recording Feature Done 6.Screen share 7.invite other users via email(Add)Done | Fixed
Pending
20 | Video Meeting | When an Android user joins a meeting as a guest, and host is a web user if the host tries to turn off the Android user’s camera access, it does not work. |  |  | Pending
23 | Video Meeting | There is a screen size/layout issue in meetings. When a user joins with a web participant, the web user’s video does not display properly. same as for screen share UI. | VideoMeetingWebCamView.jpg | Done | Pending
E) Chat
Fixed
29 | Emoji | In the Chat section, only a limited number of emojis are visible. |  | FIXED | Fixed
37 | Chats | In the chat section, when one user sends a file, the chat messages keep loading, and the document takes time to open | chat section file send in loding.mp4 | FIXED | Fixed
35 | Chats | Whenever a user sends a message to another user, a notification should appear on the screen. |  | FIXED | Fixed
26 | Start Call | In the Start Call feature, the mute option is not visible, so the user cannot see whether they are muted or unmuted. |  | FIXED | Fixed
27 | Call Duration | The call duration is shown as 0:00, and the actual duration is not being recorded. |  | FIXED | Fixed
28 | Folder>Files | When clicking multiple times to add files, the same file gets added to the folder multiple times. |  | FIXED | Fixed
30 | Edit Message | In the Chat section, even older messages can be edited. |  | FIXED | Fixed
31 | Start Call | Even when a user is offline, the “Start Call” option is shown. It should instead display “User Unavailable.” |  | FIXED | Fixed
32 | Direct Message | When clicking on Direct Message and searching by member, the member names do not appear in the dropdown. |  | FIXED | Fixed
36 | Chats | In the chat section, users cannot delete messages by; they selecting all can only delete messages one at a time |  | Done (Multi Selection Implmented) | Fixed
38 | Chats | In the chat section the features are missing on the user chat side: • Remove option • Read and Mark option | chat section missing the feature.mp4 | FIXED | Fixed
39 | Chats | Same as web app, if other member/other user deletes a message, still the user will be able to see on the chat preview |  | FIXED | Fixed
Pending
33 | Chats | When I delete a folder and notes that I created in the chat section, it does not show the name of the folder and notes that is being deleted. | Folder & Notes Error.mp4 | Same as web | Pending
34 | Chats | When an Android user deletes a team chat, it is removed from both the Android app and the web app. However, the user is not removed from the group—only the team chat is deleted. The user still appears in the group, and if any user calls this deleted group, the call still rings. |  | Please check again | Pending
40 | Chats | When replying with a document (such as an image or any other file), the document is not shown in the replied chat. |  | Done | Pending
41 | Chats | In Chats, when selecting any chat, the selected chat is not highlighted properly. | Chat Highlight issue.mp4 | FIXED | Pending
42 | chats ->Sended File | Change thisDownload File icon.jpeg on the chat to the given icon shown in the sample icon image. | Sample Icon:Download Button Icon.jpeg | FIXED | Pending
43 | Team chat | The team chat is not working in real time. When an Android user sends a message in a group, the message does not appear on the web. It only shows after refreshing the page. 1 to 1 chat working fine. |  | In progress | Pending
44 | Chat Call | If a user makes a chat call to an Android user and the Android user ends the call, the Android user leaves the call but the web user remains in the call. Similarly, if the web user ends the call, the Android user remains in the call. the call not ended for both side. |  | Testing | Pending
F) Others
Pending
46 | Initial Permissions Access Request | The app should directly ask for permissions like camera access, sms access, etc. on start of the application and there should be an optional prompt to ignore some unnecessary permissions as "do not ask again", unless the user tries to access those functions on which the system needs those accesses (such as camera, nearby devices, location, media, etc). |  |  | Pending
G) Contacts
Fixed
52 | Contact | In the Contact section, the “Created By” and “Updated By” information is not visible. |  | Testing | Fixed
54 | Contact>SMS | When sending an SMS through the Contact section, the country code is predefined as +1. If the number already includes the country code, it gets added again, resulting in two country codes. |  | Testing | Fixed
55 | Contact>Edit Contact | When editing a contact, the gender field is not being updated. |  | Done | Fixed
50 | Contact >Birth Date | In the contact section, the birth date field only allows selecting today’s date. |  | FIXED | Fixed
51 | Contact | In the Contact section, the sms icon is displayed instead of the chat icon. |  | FIXED | Fixed
Pending
53 | Contact>Activity Logs | In the Contact section, the activity logs are not showing any information. |  | Done | Pending
Super Admin
Fixed
9 | The Company->admin Login | The Super admin is not able login with the given company's admin login option | Super-Admin-UCaaS-UserActivateDeactivateExpireErr.mkv | FIXED | Fixed
16 | Companies->Virtual Number ->Filter | In the Companies -> Virtual Numbers section, the “Select DID Type” filter currently shows only two options: Local and Toll-Free. The Mobile type option is missing, and the search bar in the Select Type dropdown is not required and should be removed. |  | FIXED | Fixed
17 | Scheduled Meeting and event | When any company user schedules or creates an event, the scheduled meeting or event appears in the Video Meeting section of all companies. | Scheduled Meeting and event showing in all companies.mp4 | FIXED | Fixed
18 | Companies->Video Meetings | In the Upcoming Meetings section, the “Select Type” and “Select Status” dropdowns include a search bar, which is not required and should be removed. |  | FIXED | Fixed
7 | UCaaS Super-Admin https://admin-ucaas.mycountrymobile.com/ | In the Super-Admin UI, the admin is not able to make a user's account deactivate or expire, upon using on these functions, those user will be logged out only. and after logging in again, it will fetch some errors, but can still work with their account. | Super-Admin-UCaaS-UserActivateDeactivateExpireErr.mkv | FIXED | Fixed
1 | Video Meetings | In Video Meeting → Search Filter, when selecting the Scheduled type, no results are displayed even though meetings exist. |  | FIXED | Fixed
23 | Companies->Video Meetings | In Video Meetings, the label “Attendees” should be changed to “Invitees.” |  | FIXED | Fixed
19 | Companies->Video Meetings | In the Past Meetings section, when filtering by status “Complete,” an error popup appears saying “Something went wrong.” |  | FIXED | Fixed
5 | Companies | When Search any company in the search result the company plan name is not showing. |  | FIXED | Fixed
21 | Companies->Calls->Filter | In Companies > Calls > Filter, the “Enter Name” search is not working. |  | FIXED | Fixed
Pending
20 | Companies->Calls->Filter | In Companies > Calls > Filter > Select Date, when selecting “Last 7 Days,” records from 8 days are being displayed. |  | fixed on qa | Pending
2 | Company -> Users | create the user and select the other roles but, the created user’s role is displayed as Admin in the UCaaS application. | Create user from super admin.mp4 | FIXED | Pending
3 | Company -> Users | New created user is not assigned to the already purchased license, and the created user is not shown in the Billing Licenses section. |  | In Progress | Pending
4 | Company -> Users | When added a user from Super Admin and logs in this created user, only the Home, Phone, and Admin sections are visible after login. |  | In Progress | Pending
6 | Rate Card -> Rate Card Details | Pagination page-size selector UI issue: When clicking on the page-size dropdown, the dropdown values appear behind the table and are not visible. |  | FIXED | Pending
8 | UCaaS Super-Admin - DID numbers https://admin-ucaas.mycountrymobile.com/ | If the Super-Admn deletes a user's DID number, it does not get deleted from the user account, and still the user is able to use that DID number. | SuperAdmin-DeleteUserDIDNumber.mp4 | FIXED | Pending
10 | Company dashboard | The yearly meeting graph is not showing any report, even though the company had their meeting history. | Super-Admin-Dashboard_Yearly_meeting_report.mp4 | FIXED | Pending
11 | User's own DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin |  | DONE and need to discuss
12 | Home Dashboard | Need to rename the 'new company' as 'active company', which is not appearing on the superadmin home dashboard. |  | FIXED | Pending
13 | Companies-> Profile | When the company name is updated, the changes are not reflected in the customer portal, but still it is updated correctly in the Super Admin panel, also the company name is editable with the same name as per the other company. | Edit Company Name.mp4 | ADD VIDEO | Pending
14 | Companies->Dashboard | The company dashboard graphs are inaccurate and displaying incorrect information. |  | FIXED | Pending
15 | Companies-> Profile | In the Company Info section, the total number of members and the number of DIDs purchased are not shown properly which seems incorrect. |  | FIXED | Pending
22 | Companies->Calls->Filter | In Companies > Calls > Filter > Select Type, “Missed Calls” and “Voicemail” are not visible and are incorrectly listed under “Inbound Calls.” |  | Done | Pending
24 | Video Meetings | In the Duration column, incorrect durations are shown for all meetings (01:00 for instant meetings and 00:15 for scheduled meetings) |  | Format fixed on qa | Pending
25 | Companies->Virtual Number ->Search Bar | search bar is not working in Virtual Number section. |  | FIXED - Added search on number , name and assingTo name | Pending
26 | SMS-> search | The ‘Select Date’ dropdown is not working and shows the error message ‘Something went wrong.’ |  | FIXED on Qa | Pending
27 | SMS-> search | Search bar is not working. | Search Result in sms report.mp4 | FIXED | Pending
28 | DID Number-> assigned DID | In the search bar, searching by number is not working and no results are shown.
29 | DID Number-> Unassigned DID | In Unassigned DID section the any Unassigned DID number not showing.

## IssuesBugs of Beta version
No. | Elements/Components | Issues | Screenshots/videorec URLs | Capanicus comments | MCM Comments
Web
A. Phone
Fixed
6 | Profile-> incoming calls -> Forward Calls | Play Announcement is not working in User Profile of Phone tab. |  | FIXED | Fixed
Pending
1 | call transfer to extension | When a call is made from the UCaaS web to a non-UCaaS number and then transferred to another UCaaS extension, the call connects successfully. Charges are deducted for the first user’s call log and charges are correct, but charges for the second user (extension transferred call recipient) are not shown in the call-log report. |  | Pending | Pending
2 | transfer call report on external number | When the user transfers the call to an external number, the call duration and cost is not being considered on the master caller's call report. |  | Pending | Pending
3 | Call Merge | The MasterCaller stucks at call when all other recipiants are left. |  | couldnt reproduced | Pending
4 | Dialer search bar | The user should be able to search saved contacts on the dialer, including users with their extension and contact number(which is added in user details). |  | Improvement | Pending
5 | Recordings Charge | Need to implement call recordings charge on companies user base capping, and storage should be allotted differently |  | In Progress | Pending
7 | Sentiment Analysis | The Sentiment analysis is not working as expected. |  | Need to Discuss | Pending
8 | Voicemail Timeout issue | The voicemail stays longer than 30 seconds. |  | As discussed with tauseef Sir there is no logic to end the voicemail after 30 sec even the caller is leaving the message.. but it happens when no one speaks for 3 to 4 sec it will be disconected | Pending
9 | Decline with message | On Inbound calls, Decline with message is not working, SMS cost prompt and DLC required(if needed) restriction shall be shown to the user. |  | FIXED | Pending
10 | Free Call Minutes | Call charges are being deducted even after the free call minutes are finished. |  | Testing | Pending
11 | Call Recording Deletion | if the recording storage is free, we'll delete all recordings after 7 days after notifying the user before certain time. |  | Confirmation pending from furkan sir | Pending
12 | transfer calls | when the user does an extension call and then the same caller transfers the extension call to another extension, all calls will be disconnected immediately. |  |  | Pending
13 | monitoring | In the Monitoring section, most features are not functioning correctly. Only Listen and Barge are available, and within Barge, functions like Mute, Transcripts, Hold, and others don’t work. The Campaign section shows no reports, and even when a campaign is opened, it still displays Monitoring – Call Queue at the top. Overall, the sections are not working properly. |  |  | Pending
14 | Transcription | System does not keep transcription on when user close the Call UI and get back to transcription. |  | FIXED | Pending
15 | Transcription in Hindi | Transcription in Hindi is not working now |  | Saurabh Please provide Azure details | Pending
16 | Call Monitoring | Except All Calls, All other call monitoring tabs are not working, also call queue waiting callers records are being stuck on tab |  |  | Pending
17 | Call Dialer | Need to implement Phone Number Format with Country Code: +1 (555) 123-4567 |  | FIXED | Pending
18 | call recoring on in-coming call | On incoming calls, call recording starts automatically even when the call recording setting is disabled. |  |  | Pending
| Phone | The transcript or recording feature is not working on phone |  |  | Pending
| call merge | Call merge is not working. |  |  | Pending
| incoming calls | Incoming calls are not working. |  |  | Pending
| Call history | Call history does not display after calling |  |  | Pending
B. Chat
Fixed
16 | Chat Delete access | If the user does not have access to delete, the user still can delete chats via team, favorites and direct tab | detele all chat.mp4 | FIXED | FIXED
17 | Chat Reload Issue | sometimes the user cannot see previous messages and even previous does not reload automatically until the user refreshes the page |  | FIXED | FIXED
18 | Chat Reload and Jump to Bottom | To stabilize the feed, implement a top-loading spinner combined with CSS overflow-anchor: auto to prevent the view from jumping when older messages prepend. Additionally, add a floating "down-arrow" button that appears when the user scrolls up, providing a one-click shortcut to return to the latest message. | https://capanicus.slack.com/files/U09S8RH17J5/F0AAKHXP71Q/chatloadingandjumptobottom.png | FIXED | FIXED
19 | Click on Created folder | If the user clicks on created chat folder name via vague notification, then gets back on chat, the user will be redirected to the top of the chat. |  | FIXED | FIXED
20 | Chat> Click on Replied Message | Sometimes, when clicking on a reply message, it does not redirect to original message and instead shows the notification: ‘Original message not found. It might be in an older conversation.’ |  | FIXED | FIXED
23 | chat->folder | There is no character limit on note and folder names. |  | FIXED | FIXED
25 | Join Call Button | Join button which was removed, is still pending to connect ongoing team chat call. |  | FIXED | FIXED
28 | Chat | While editing a message draft in one chat, switching to a different chat carries the same edited draft into the other chat. When the draft is sent, it is delivered to the original chat instead of the currently active chat. | recording.webm | FIXED | FIXED
30 | Chat > NOTES | Deleted note activity redirects to notes instead of showing deleted state. Also group or team does not shows as it is whether the team name is in UPPERCASE or lowecase style | Team or group Name does not shows as it is written uppercase and lowecase and second notes after deletion, edited.mp4 | FIXED | FIXED
31 | Team Chat> removed/left user | In a team group, if any user is removed or leaves the group, their name and profile avatar are not shown in their previous chat messages. | Removed/left user chat message issue.mp4 | FIXED | FIXED
29 | Chat > adding notes | Formatting option labels are visible for a few milliseconds before the notes editor loads properly. | UI flicker in notes.webm IMAGE: UI notes lable name shows while it is loading .png |  | FIXED
32 | Reply chat | When replying to a message in one user’s chat and then opening another user’s chat, the typed reply message appears in the other user’s chat. | Reply message issue.mp4 | FIXED | FIXED
Pending
21 | Chat>message | When typing a long message in the chat input field, pressing Shift + Ctrl to move to a new line instead moves the cursor directly to the bottom line. |  | In Progress | Pending
| Team Chat> Deleted user | If a user is deleted, their name and profile avatar are not shown in their previous chat messages in the team group. | Deleted user profile name avatar issue.mp4 |  | Pending
24 | Chat AI Assistant | A chat AI assistant shall be included for user's quick & easy issue resolution as per the FIgma design given in "Screenshots/videorec URLs" column |  | Please provide video or Screenshot | Pending
26 | Chat Section | A member cannot ping/tag other members on team chat (for example, @admin) |  | In Progress | Pending
27 | chat | the change group photo not available after creating a group. |  | In Progress | Pending
22 | chat->emoji | There are some categories of emojis are missing, e.g., flags, |  | In Progress | Pending
| Chat list | chat pic profile |  | NEED TO DISCUSS | Pending
| In Team Delete message | In Team group if any user delete chat message name of the user is not showing, who is deleted the message is not showing. | delete message chat UI.png |  | Pending
| Chat Section | Error appears when sharing image in chat |  |  | Bushra - pending
C. Video Meeting
Fixed
33 | Join Meeting Via Link | If an unknown user joins the meeting via the URL link and enters only spaces in the Name field, the user is still able to join the meeting. |  | FIXED | FIXED
Pending
|  | In the video meeting, when I click the recording button, a popup appears saying 'Recording stopped |  |  | Pending
34 | video - recording | When I click the recording icon during a meeting, it loads and starts recording, but the recording info—like how long it has been recording—doesn’t show. |  | FIXED | Pending
35 | Video Improvement Part | Suppose I scheduled a meeting for one hour later and switch to another tab to work. When the meeting time arrives, I should receive a system notification. However, no system notification is received. |  | FIXED | Pending
36 | join buttton in notification secction | Add a "Join" button in the notification section to directly join a meeting when invited. |  | FIXED | Pending
37 | join meeting multiple time | A user can join the same meeting multiple times from different tabs using the same ID and name, which is not expected behavior and should be fixed. 1. There is no user validation on checking if the user is already on a video call. | recording.webm | FIXED/ Lets Discuss this on call. | Pending
| Video Meeting | Unable to join meeting via UCCAS site, but can join through email link | https://drive.google.com/file/d/1OXWeljrBszsz2kmiOPKzla4ndPlVMEkD/view?usp=sharing |  | Pending
E. Home
Pending
40 | Campaign Dashboard | In the campaign dashboard, the agent report displays the wrong count of campaigns assigned to agents. |  | Please add video Couldn't reproduced | Pending
F. User Settings
Fixed
41 | Settings - Video | When we set profile photo from android, on the web version, the user won't be able to remove that profile photo |  | FIXED | FIXED
G. Admin Section
Pending
Pending | Pending | Pending | Pending | Pending | Pending
Pending | Pending | Pending | Pending | Pending | Pending
Pending | Pending | Pending | Pending | Pending | Pending
Pending | Pending | Pending | Pending | Pending | Pending
Pending | Pending | Pending | Pending | Pending | Pending
Pending | Pending | Pending | Pending | Pending | Pending
I. Campaign
Fixed
49 | Campaigns Reports | In some campaigns the notes are visible even when the call is getted cut |  | FIXED | FIXED
48 | Campaign >Campain Logs | In campaign call reports, the Notes option appears for certain calls even when the call status is Cancelled. |  | FIXED/ Please check this | FIXED
Pending
47 | Dialed Numbers | After running the campaigns the connected calls number is not visible |  | (Working fine with not anwered), Unable to check answered (webhook issue) TESTING | Pending
50 | Create Campaign | While creating a campaign in media before submitting the campaign settings when the user changes the dialer the script is removed from it and during the campaign calls the script is empty. | campaign script.webm | Not an issue : We kept type in Script based on the dialer : When dialer is changed the Script will also should be selected as per dialer chosen. | Pending
51 | Campaign>Recording | When an agent does not have recording access at the agent level, call recording does not work during a campaign, even if recording is enabled in the campaign settings. | Campaign Call recording issue.mp4 | Discussed with Adnan.. | Pending
I) Inbox
Fixed
69 | SMS-Search bar | The search bar is not working. |  | In Progress | FIXED
55 | Inbox > SMS Tab | Add search functionality in Message Inbox to find contacts by name or number |  |  | FIXED
57 | SMS -> Message | In the Inbox, when I try to send a message to any number, a “"available_balance" is not allowed” pop-up appears, and the SMS is not sent. |  | Add video | FIXED
81 | Sms > Plans > Free SMS | Free SMS are not being deducted from given free SMS in plan -> Billing. |  |  | FIXED
Pending
70 | SMS-Search bar | names wth numbers saved in contacts and numbers used on which SMS are sent shall be visible on the search bar including users with their contact number(which is added in user details).. |  | Discuss | Pending
53 | SMS -> Message | When I send an SMS from the inbox, I get a popup message saying 'SMS sending failed |  | FIXED | Pending
56 | SMS -> Message | Delivery Status Missing: The system does not notify if the SMS is sent, delivered, or failed.UCAAS |  | FIXED | Pending
| SMS | SMS messages are not being sent in the SMS section |  |  | Pending
54 | Inbox > SMS | Contact profile picture is not displayed in Inbox conversation list or contacts | Contact profile picture issue.mp4 | FIXED/ Please check again working fine | Pending
| Inbox | Inbox index section layout misaligned | https://drive.google.com/file/d/1bg9P9NfM8axwIcAlCSWsWnSVYBArG4_n/view?usp=sharing |  | Pending
J) Contacts
Pending
81 | Contacts and Search bar | Users shall be added with their contact numbers and other info (which is added in user details). |  |  | Pending
| update same contact issue | If a new contact is created for the first time in any company and the same contact is later created in another company, when the contact is updated, the username of the user who created it in the first company is shown on the updated contact. | contact Update issue.mp4 |  | Pending
| contact | I don’t have a DID number, but when I try to call from contacts, the call goes through and then shows “trying to call on this number is not available.” | https://drive.google.com/file/d/1tR6igIA-7Spspw8DTOFDjczZKBFWf6iC/view?usp=sharing |  | Bushra Pending
K) DID Numbers
Fixed
|  | Added inventory numbers shall have their available features(sms/calls in/out) |  | FIXED | Umar/Fixed
Pending
While purchasing the DID, user shall see those features before billing parts.
58 | Billing -> Plan | Billing → Plan → DID(s) tab, the cost of purchased DIDs is not displayed. | DID cost.mp4 | FIXED | New purchased DIDs cost showing already purchased DIDs cost not showing
| Add User -> assign number | if creating bulk users(e.g more then 2 or 3 ) and assigning their DID numbers using the ‘Assign Now’ option after payment, the same DID is being added two-three times. | Same DID Assign two to three time.mp4
| Add/Assign Same DID Number issue | Users from different companies are able to purchase and assign the same DID numbers at the same. | Assign and purchesing same did issue.mp4
| Number | When I purchase a DID number, it shows ‘Something went wrong |  |  | Bushra Pending
M) Others
Fixed
65 | Error 404 | Sometimes the Error 404 occurs on some accounts, on which upon clicking "Go To Homepage", The button does not redirect and refresh up on homepage | ClickOnHomepageRedirectionErr404.mp4 | FIXED | Anusha/Fixed
66 | Account Renewal | all users except admin, are able to login and use all functions(excluding billing related). |  |  | Anusha/Fixed
60 | Knowledge base DB Collision | some companies are having the same knowledge bases created on a single company, this means all knowledge base records are being unified in several companies: |  | FIXED | Umar/Fixed
61 | Login OTP | There should be an OTP attempt limit, for example: if the user is not able to insert otp correctly for 5 times |  | FIXED | Umar/Fixed
62 | Login OTP | There is no otp expiration rule, such as after 10-15 mins the otp shall expire. |  | FIXED | Umar/Fixed
Pending
| Deleted user visibility | Deleted users must not be visible in any actions, such as i) While starting a new chat or creating/editing team chat. ii) Users/Inventory/departments lists iii) Licence management list iv) DID inventory list(assigned DID will be un-assigned) v) IVR/Call Queues/any Forward to extension actions. vi) Any search bars, if it includes a separate users list. |  | FIXED | Anusha/Not Fixed
| ai | ai tools not working |  |  | shailendra - pending
59 | Password Reset Link Has No Expiration Time v1.2.8 | There is no time limit or expiration for the password reset link, as it remains valid regardless of when it is opened, though once used password reset link, will be expired when the user uses on second time, but it should notify as expired at initial screen after trying to use it second time. |  | FIXED/ Please explain which Scenario u are reffering to is not fixed or add video | Not Fixed
63 | User owned DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin |  | Improvement | Anusha/Not Fixed
64 | Overall UI responsiveness | When the user/admin does any change for another user, such as changing their role, creating a department or team chat and adding a scheduling and inviting other users/members, etc. The bug is that the application is not implementing real-time data updates and relies on manual page refreshes, which is an issue with frontend or backend communication, possibly a missing or improperly configured WebSocket connection, incorrect event handling, or issues with a live-reloading development server. The UI needs a mechanism like WebSockets or AJAX calls to listen for server-sent events and update the display dynamically, rather than waiting for the user to manually refresh |  | FIXED | Anusha/Not Fixed

## UI Design Changes(UDC)
ID | Module | Improvement | Figma / Assets | Dev Status | PR / Build # | Capanicus Comments | MCM Comments
1 | ADMIN Setup | Need to add ADMIN Setup UI when the ADMIN user logs in for the first time | Phone Settings(Mainly Caller ID assignment and default functions creation applied): https://gemini.google.com/share/e08a245d2507 AI Agent creation: https://gemini.google.com/share/41262c667fc1 | In Review/Pending | v1.2.8
2 | ADMIN -> Phone Systems | Need to integrate Basic info, General, Call Rules, etc in ADMIN-> Phone Systems with as one section named "Preferences", sample design is given in the 'Figma/Assets' | https://gemini.google.com/share/1898521d2f27 | In Review/Pending | v1.2.8
3 | ADMIN -> Company info | Need to redesign the "Company info" tab with renaming it as "Accounts & Sites" | https://gemini.google.com/share/9cdee8d976a2 | In Review/Pending | v1.2.8
4 | ADMIN -> Users | Need to redesign the "Users" tab | https://gemini.google.com/share/afa3d79e4e3e | In Review/Pending | v1.2.8
5 | ADMIN -> AI Tools | Need to redesign the "AI Tools" tab | https://gemini.google.com/share/ec95d037c8e6 https://gemini.google.com/share/479a52f16980 | In Review/Pending | v1.2.8
6 | Text-To-Speech | Need to Redesign the text to speech and improve functionality | https://gemini.google.com/share/a17aaafaf3ad | In Review/Pending | v1.2.8
7 | Home Dashboard | Need to add interactive and visually informative dashboards for all utilities/functions | https://agent-insight-hub.replit.app/ | In Review/Pending | v1.2.8
8 | Overall UI | Need to add well-informative, understandable guidelines and (i) icons as provided in the previous designs for all required functionalities such as on Call Queues, IVRs, Departments, Shared Line, Sites, Users/Extensions, Roles, etc lists and creation. |  | In Review/Pending | v1.2.8
9 | ADMIN | Here are some descriptions which need to be added in respective function creations: 1. New Users: Each additional user requires a separate monthly subscription. Your monthly total will increase based on the features and services assigned to this new user. 2. New Role: Create a custom role, Create a custom role to control what your team members can see and do. Select a starting point (like Manager or Agent) to automatically pre-fill recommended permissions, then fine-tune their access below. 3. Add Additional number: Adding an additional number to an existing user/plan will only incur a charge for the phone number itself. This action does not create a new subscription or user plan. Your monthly recurring total will be updated based on the quantity of numbers added. 4. New site ;Use this feature to add different office locations or branch sites for your company. This allows you to group users by their specific location (e.g., London, Dubai, or Singapore) while keeping everything under one central billing account. 5. New Department:Create a department to organize your company’s workflow. This allows you to route calls to specific teams (e.g., Support or Billing) and assign multiple users to a single extension so they can handle incoming calls together. 6. Add a call queue:Set up call queues at the Company level or for Individual Site locations. This allows you to organize incoming traffic for specific branches, ensuring callers are held professionally until a user from that site is ready to answer. 7. New IVR MENU:Use this to build your automated menu. After creating your IVR here, you can assign it to any Phone Number in your system to manage greetings, routing, and voicemail messages automatically. 8. New Shared line: Multi-Department Sharing, this feature to link one or more departments to a single shared line. This creates a unified communication point where all assigned departments can manage calls from the same number simultaneously. |  | In Review/Pending | v1.2.8
10