## Web
| Elements/Components | Issues | Screenshots/videorec URLs | Capanicus comments | MCM Comments
A. Phone
1 | call transfer to extension | When a call is made from the UCaaS web to a non-UCaaS number and then transferred to another UCaaS extension, the call connects successfully. Charges are deducted for the first user’s call log and charges are correct, but charges for the second user (extension transferred call recipient) are not shown in the call-log report. |  | Testing | Umar - Pending
2 | transfer call report on external number | When the user transfers the call to an external number, the call duration and cost is not being considered on the master caller's call report. |  |  | Anusha - Pending
3 | Call Merge | The MasterCaller stucks at call when all other recipiants are left. |  | when master caller hang then all other hang , if master call not hang he will still be able to add more calls | We need to discuss this with furqan sir.
4 | Dialer search bar | The user should be able to search saved contacts on the dialer, including users with their extension and contact number(which is added in user details). |  |  | Saurabh - Pending
5 | Recordings Charge | Need to implement call recordings charge on companies user base capping, and storage should be allotted differently |  | Improvement | Saurabh - Pending
6 | Profile-> incoming calls -> Forward Calls | Play Announcement is not working in User Profile of Phone tab. |  | Testing | Jay - Pending
7 | Sentiment Analysis | The Sentiment analysis is not working as expected. |  |  | Saurabh - Pending
8 | Voicemail Timeout issue | The voicemail stays longer than 30 seconds. |  |  | Bhushra - Pending
9 | Decline with message | On Inbound calls, Decline with message is not working, SMS cost prompt and DLC required(if needed) restriction shall be shown to the user. |  |  | Saurabh - Pending
10 | Free Call Minutes | Call charges are being deducted even after the free call minutes are finished. |  |  | Saurabh - Pending
11 | Call Recording Deletion | if the recording storage is free, we'll delete all recordings after 7 days after notifying the user before certain time. |  | Improvement
12 | transfer calls | when the user does an extension call and then the same caller transfers the extension call to another extension, all calls will be disconnected immediately. |  |  | shailendra - pending
13 | monitoring | In the Monitoring section, most features are not functioning correctly. Only Listen and Barge are available, and within Barge, functions like Mute, Transcripts, Hold, and others don’t work. The Campaign section shows no reports, and even when a campaign is opened, it still displays Monitoring – Call Queue at the top. Overall, the sections are not working properly. |  |  | shailendra - pending
14 | Transcription | System does not keep transcription on when user close the Call UI and get back to transcription. |  |  | saima - pending
15 | Transcription in Hindi | Transcription in Hindi is not working now |  |  | Saurabh - Pending
16 | Call Monitoring | Except All Calls, All other call monitoring tabs are not working, also call queue waiting callers records are being stuck on tab |  |  | Saurabh - Pending
17 | Home/Status presence on DND | The status presence on DND does not work as instructed. |  |  | Umar/Fixed
18 | Call forwarding | When the user has set the calls on external numbers, and if the transferred call is declined, still the external number will get the call second time just after the IVR. |  | Issue with provider, not getting bye back frmo external number | Saurabh - Fixed
19 | Call Queues | Call Queue Function is not working neither via DID not via IVR. |  |  | Saurabh - Fixed
B. Chat
16 | Chat Delete access | If the user does not have access to delete, the user still can delete chats via team, favorites and direct tab | detele all chat.mp4 | FIXED ON DEV | shailendra - pending
17 | Chat Reload Issue | sometimes the user cannot see previous messages and even previous does not reload automatically until the user refreshes the page |  |  | shailendra - pending
18 | Chat Reload and Jump to Bottom | To stabilize the feed, implement a top-loading spinner combined with CSS overflow-anchor: auto to prevent the view from jumping when older messages prepend. Additionally, add a floating "down-arrow" button that appears when the user scrolls up, providing a one-click shortcut to return to the latest message. | https://capanicus.slack.com/files/U09S8RH17J5/F0AAKHXP71Q/chatloadingandjumptobottom.png |  | shailendra - pending
19 | Click on Created folder | If the user clicks on created chat folder name via vague notification, then gets back on chat, the user will be redirected to the top of the chat. |  |  | Saurabh - Not fixed
20 | Chat> Click on Replied Message | Sometimes, when clicking on a reply message, it does not redirect to original message and instead shows the notification: ‘Original message not found. It might be in an older conversation.’ |  | FIXED ON DEV | shailendra -Not fixed
21 | Chat>message | When typing a long message in the chat input field, pressing Shift + Ctrl to move to a new line instead moves the cursor directly to the bottom line. |  |  | shailendra -Not fixed
22 | chat->emoji | There are some categories of emojis are missing, e.g., flags, |  | improvement | shailendra - pending
23 | chat->folder | There is no character limit on note and folder names. |  | FIXED ON DEV | Partially fixed ,Still in notes no character limit is there
24 | Chat AI Assistant | A chat AI assistant shall be included for user's quick & easy issue resolution as per the FIgma design given in "Screenshots/videorec URLs" column |  |  | shailendra - pending
25 | Join Call Button | Join button which was removed, is still pending to connect ongoing team chat call. |  |  | shailendra - pending
26 | Chat Section | A member cannot ping/tag other members on team chat (for example, @admin) |  |  | shailendra - pending
27 | chat | the change group photo not available after creating a group. |  |  | shailendra - pending
28 | Chat | While editing a message draft in one chat, switching to a different chat carries the same edited draft into the other chat. When the draft is sent, it is delivered to the original chat instead of the currently active chat. | recording.webm |  | saima - pending
29 | Chat > adding notes | Formatting option labels are visible for a few milliseconds before the notes editor loads properly. | UI flicker in notes.webm IMAGE: UI notes lable name shows while it is loading .png |  | Jay - Pending
30 | Chat > NOTES | Deleted note activity redirects to notes instead of showing deleted state. Also group or team does not shows as it is whether the team name is in UPPERCASE or lowecase style | Team or group Name does not shows as it is written uppercase and lowecase and second notes after deletion, edited.mp4 |  | Jay- Pending
31 | Team Chat> removed/left user | In a team group, if any user is removed or leaves the group, their name and profile avatar are not shown in their previous chat messages. | Removed/left user chat message issue.mp4 |  | Umar/Pending
32 | Reply chat | When replying to a message in one user’s chat and then opening another user’s chat, the typed reply message appears in the other user’s chat. | Reply message issue.mp4 |  | Umar/Pending
1 | Overall Omnichannel Chats | The agent has to change/refresh chats to see updated messages on whatsapp, facebook, etc |  |  | Saurabh - Fixed
2 | Chat Delete access | If the user does not have delete chat access, still can delete chat messages via sending texts with documents |  | FIXED ON DEV | shailendra - fixed
4 | Chat Unread Tab | already read chats cannot dissappear, Until the user clicks of mark as read. |  | already working | shailendra - fixed
5 | Chat Unread Tab | Until the user is in unread chats section, the user cannot get new messages in it. |  | already working | shailendra - fixed
6 | Team Chat Creation | The user is able to create multiple team chats on clicking send while team chat creation. |  | FIXED ON DEV | shailendra - fixed
7 | Edit Team Chat | Some existing users are not visible on edit team chat function, also upon checking add members list, those invisible members are shown to add again. |  | already working | shailendra - fixed
10 | Edit chat message | cancelled edit message cannot be removed upon clicking. |  |  | Umar/Fixed
11 | Edit message preview | when edit the message the edited message is not showing in the chat preview. | chat preview edit message.png | FIXED ON DEV | shailendra - fixed
13 | Chat edited Message | On the receiver’s side, the edited message is not shown as edited. |  | FIXED ON DEV | shailendra - fixed
15 | Chat> Reply Message | When a text message is sent and then replied to with an image, on the receiver’s side the image message appears in blue, as if it was sent by the receiver. |  | FIXED ON DEV | shailendra - fixed
19 | chat->delete message | You can delete a message for yourself or for everyone in the chat, but after deletion, nothing is shown. It should display a notice like ‘This message was deleted,’ but it doesn’t. |  | FIXED ON DEV | shailendra - fixed
23 | chat section | upon clicking on pop up notifications, app-system does not redirect to the particular chat destination, also sometimes the popup notification does not work. |  |  | shailendra - fixed
25 | chat-> call | In the chat section, when a call is rejected, it doesn’t show the username; it just says .The user declined the call. |  | FIXED ON DEV | shailendra - fixed
C. Video Meeting
33 | Join Meeting Via Link | If an unknown user joins the meeting via the URL link and enters only spaces in the Name field, the user is still able to join the meeting.
34 | video - recording | When I click the recording icon during a meeting, it loads and starts recording, but the recording info—like how long it has been recording—doesn’t show. |  |  | Pending/Bushra
35 | Video Improvement Part | Suppose I scheduled a meeting for one hour later and switch to another tab to work. When the meeting time arrives, I should receive a system notification. However, no system notification is received. |  | improvement | Pending/Bushra
36 | join buttton in notification secction | Add a "Join" button in the notification section to directly join a meeting when invited.
37 | join meeting multiple time | A user can join the same meeting multiple times from different tabs using the same ID and name, which is not expected behavior and should be fixed. 1. There is no user validation on checking if the user is already on a video call. |  |  | Pending/ Bushra
38 | Video Improvement Part | Suppose I have scheduled a meeting for one hour later, and due to some work I am using another tab, then I should receive a system notification saying that the meeting time has arrived. |  | improvement | Pending/ Bushra
39 | Video Meeting | A user can join the same meeting multiple times from different tabs using the same ID and name, which is not expected behavior and should be fixed. | recording.webm |  | Pending/ Bushra
36 | schedule - Meeting Topic | When we schedule a meeting in that meeting topic there is no character limitations. |  | FIXED ON DEV | fixed/Bushra
37 | feedback | After the meeting ends, if a user submits a long feedback message, the typing stops after a few lines and the user is unable to type anything further. No warning or error message is shown. Additionally, when the host checks the feedback, long feedback text overflows outside the container. |  | FIXED ON DEV | Fixed/Bushra
39 | video - share recording | After recording a meeting, the recording can only be shared with participants who were in the meeting; it cannot be shared with others outside the meeting. | share video recording.png | FIXED ON DEV | Fixed/ Bushra
40 | meeting - host | When the host leaves their own meeting, the remaining participants are incorrectly assigned the host role and displayed as the host. |  | FIXED ON DEV | Fixed/ Bushra
41 | create scheduling meeting | Sometimes, while scheduling a new meeting, after filling in all the details and clicking the Schedule Meeting button, an error popup appears but it is blank. No error message is displayed. | create meeting 02.png | Not able to reproduce | Fixed/ Bushra
43 | meeting password | There is no password limit when scheduling a meeting. Because of this, the UI breaks—users can enter very long passwords, which overflow outside the container. | meeting passwordd.png | FIXED ON DEV | Fixed/ Bushra
44 | approve / left user | When someone joins a meeting, the host receives an approval message with Accept or Decline options. However, when a participant leaves the meeting, no message is displayed. |  | FIXED ON DEV | Fixed/ Bushra
33 | Video | during the video meeting Recording is not working |  | already working | Fixed/ Bushra
34 | past meetinng | There is a UI issue in past meeting feedback When I send a long feedback, the feedback text overflows outside the box. | feedback issue.png | FIXED ON DEV | Fixed/ Bushra
35 | Video | When we attend the meeting through meeting id and url there is no record that we had attended the meeting and in that feedback given is also not shown anywhere . |  | AW: it show all the information in the Past Meeting tab | Fixed/ Bushra
36 | Video Meeting | When we schedule a meeting in that meeting topic there is no character limitations. |  | FIXED ON DEV | Fixed/ Bushra
37 | Video Meeting | There is no limitations in password while scheduling a meeting . |  | FIXED ON DEV | Fixed/ Bushra
38 | Video Meeting | User Profile > Personal Video Meeting Link 404 Error. When copy and and paste url on new tab of browser does not works. |  | FIXED ON DEV | Fixed/ Bushra
40 | Video Meeting and My Recordings | The user is not able to access their own recordings from my recording section | Meeting-MyRecordings.mp4 | already working | Fixed/ Bushra
E. Home
40 | Campaign Dashboard | In the campaign dashboard, the agent report displays the wrong count of campaigns assigned to agents.
4 | Campaign Dashboard | In the campaign dashboard, the number of calls made is displayed incorrectly. |  | Working already (No fix required) | Anusha/ Fixed
F. User Settings
41 | Settings - Video | When we set profile photo from android, on the web version, the user won't be able to remove that profile photo
4 | Settings - Phone | After the new updates, on the new user creation, user's status resets and none of them will be selected by default as per the user had set before the updates, due to this the inbound calls are being failed. Sometimes, the older user has to wait to get online status |  | Working already (No fix required) | Umar/Fixed
G. Admin Section
42 | Call Queues Creation | The custom made user role can't be the manager of a Call Queues, despite giving all permissions to that user role |  | discussed with raman
43 | admin - sms/calling rates | In Admin Settings → SMS/Calling Rates, only Outbound Rates are shown, without clearly indicating whether they are for SMS or calling. After selecting a country, landline and mobile rates appear, but SMS or calling is still not specified. Also, searching for Canada shows two landline rates. |  | need to discuss
44 | IVR Function | The overall IVR UI is not user friendly and does not seem professional and has some Logical bugs, the media function development is not completely implemented, where the user should have features to make the text to speech audio in multiple voices and accents, sample designs are given in "Screenshots/videorec URLs" column | Sample image 1.jpeg Sample image 2.jpeg
45 | IVR Function | The Generic Key press function does not work on IVR calls, such as if the IVR is set on pressing * to go back on previous menu and # to repeat the present menu, also there is not option for 0 digit keypress | IVR Previous and Repeat Manue.mp4
46 | User ID | multiple systems with a single user ID can call different users without knowing each other.
42 | Voice Agent | There is no validation on system prompt field the agent created without system prompt then edit this and click on update the "systemPrompt" is not allowed to be empty error message showing. |  | FIXED ON DEV | Umar/Fixed
44 | Admin -> Company Info | I went to Company Info under Admin and created a new site. The site was created successfully, but when I try to delete it, it does get deleted; however, the name does not appear while it is being deleted. | Notification Error.webm | fixed on dev | Umar/Fixed
49 | ADMIN<Company info | I went to Company Info under Admin and created a new site. The site was created successfully, but when I try to edit site name and address then it gives error such us "caller_id_name" must be a string. | recording.webm | fixed on dev | Umar/Fixed
I. Campaign
47 | Dialed Numbers | After running the campaigns the connected calls number is not visible |  | (Working fine with not anwered), Unable to check answered (webhook issue) | Anusha/Not Fixed
48 | Campaign >Campain Logs | In campaign call reports, the Notes option appears for certain calls even when the call status is Cancelled. |  |  | Anusha/Pending
49 | Campaigns Reports | In some campaigns the notes are visible even when the call is getted cut
50 | Create Campaign | While creating a campaign in media before submitting the campaign settings when the user changes the dialer the script is removed from it and during the campaign calls the script is empty. | campaign script.webm | add video | Video Added
51 | Campaign>Recording | When an agent does not have recording access at the agent level, call recording does not work during a campaign, even if recording is enabled in the campaign settings. | Campaign Call recording issue.mp4 | Need clarification | Video Added
52 | Predictive Dialer | In the predictive campaign, the call is placed to the customer, but it disconnects as soon as the customer answers. |  |  | Fixed.But transcription is still in load
67 | xlsx Leads | if we upload the xlsx leads file with proper headers then it show me the error regarding headers. | Upload xlsx Lead File Header Error.mp4 | working | Fixed
51 | Campaign>Disposition logs | In disposition logs when the user select disposition in more there is no scrollbar to see the selected disposition | disposition logs.webm | fixed on dev | Anusha/Fixed
52 | Campaign >Campain Logs | In campaign calls, when the call does not connect, the status should be Failed, but it is shown as Cancelled. | failed status.webm | fixed on dev | Anusha/Fixed
54 | Preview campaign call | After completing all lead calls, the status still shows Paused/Running instead of Completed. | campaign call.webm | Working already (No fix required) | Anusha/Fixed
55 | PopUpNotification->Preview Dialer | During preview dialer calls when we skip a contact the popup is not coming like "contact is skipped" | skip contact.webm | fixed on dev | Anusha/Fixed
56 | Notifications->Leads | When we add a lead in existing group the notification is contact saved successfully but it should be "contact moved successfully". | Notification leads.webm | fixed on dev | Anusha/Fixed
57 | Notification->Campaignlist | While updating the campaign leads the notification is "campaign created successfully", its not showing which campaign is updated and the updated message. | campaignlist.webm | fixed on dev | Anusha/Fixed
58 | Notification->Campaign->Call Script | When we update the call script the popup should come "Script updated successfully" but it is appearing "script saved successfully". | call script.webm | fixed on dev | Anusha/Fixed
59 | Notification->Campaign->Call Script | In Call script ,when we want to delete a script the delete icon is not there . | delete icon.webm | fixed on dev | Anusha/Fixed
60 | Notification->Leads | When deleting leads, a popup appears with the message “Contacts saved successfully,” which is incorrect. | deleting leads.webm | fixed on dev | Anusha/Fixed
61 | Notification->Leads | During lead upload, the popup message “Contacts saved successfully” is displayed instead of a relevant upload message. | uploading leads.webm | fixed on dev | Anusha/Fixed
62 | Notification->Leads | When editing leads, no popup notification is shown. | editing leads.webm | fixed on dev | Anusha/Fixed
63 | Notification->Leads | When adding a contact from the Leads section, the popup notification is not displayed. | add contact.webm | fixed on dev | Anusha/Fixed
64 | Notification->Leads | When changing the lead header name, a popup appears with the message “Leads saved successfully.” | lead header.webm | fixed on dev | Anusha/Fixed
65 | Campaign List | The Campaign List page is not displaying pagination correctly. It is fixed at 25 records, and additional page numbers are not visible. | campaign list ui.webm | fixed on dev | Anusha/Fixed
68 | Campaign Logs | When the screen is 100% in campaign logs the action button are not visible |  | fixed on dev | Anusha/Fixed
I) Inbox
69 | SMS-Search bar | The search bar is not working.
70 | SMS-Search bar | names wth numbers saved in contacts and numbers used on which SMS are sent shall be visible on the search bar including users with their contact number(which is added in user details)..
53 | SMS -> Message | When the sms is sent from report a popup occurs no sufficient balance to send message but by clicking in confirm the message is sent
54 | Inbox > SMS | Contact profile picture is not displayed in Inbox conversation list or contacts | Contact profile picture issue.mp4 |  | Umar - Not Fixed
55 | Inbox > SMS Tab | Add search functionality in Message Inbox to find contacts by name or number |  |  | Umar/partially fixed Its added but not working.
56 | SMS -> Message | Delivery Status Missing: The system does not notify if the SMS is sent, delivered, or failed.UCAAS |  | Is it done from SMS local..? and part of improvement | But that's a mandatory function which other SMS apps provides.
57 | SMS -> Message | In the Inbox, when I try to send a message to any number, a “"available_balance" is not allowed” pop-up appears, and the SMS is not sent. | inbox issue.mp4 | Add video | shailendra - pending
68 | SMS -> Message | When an SMS is sent from the Report → Phone section, if the phone number is not saved, it appears twice for the same number. |  |  | Umar/Fixed
70 | Inbox > SMS | The system allows the user to send blank messages containing only spaces. |  | fixed on dev | Umar/Fixed
73 | SMS -> Message | In the SMS section, messages are being sent and charges are deducted, but the recipient is not receiving the SMS. |  |  | Umar/Fixed
74 | Report->SMS Logs | While sending the SMS, the displayed charge is 0.02, but in the SMS logs it is showing 0.03. |  | Please attach screenshot or video to check the same entry and create the scenrio | Umar/Fixed
76 | SMS -> Message | SMS charges are being deducted only when messages are sent from the SMS tab. When SMS is sent from the Contacts section, the charges are not being deducted and are showing as 0.00. |  |  | Umar/Fixed
79 | Sms-> Emoji | The emoji sended in sms the char count is 2 for one emoji |  | It works like this only you can raise this to tauseef or pankaj in call | Umar/Fixed
80 | Sms > Inbox sms Lists | When the number of SMS contacts exceeds the visible area in the SMS inbox, the contact list does not show a scrollbar, and the user is unable to scroll down to view all SMS contact entries. | Sms conversation contact list scroll bug.png |  | Anusha/Fixed
81 | Sms > Plans > Free SMS | Free SMS are not being deducted from given free SMS in plan -> Billing.
J) Contacts
81 | Contacts and Search bar | Users shall be added with their contact numbers and other info (which is added in user details).
78 | Contact > Contact Activity | The date picker should allow direct year and month selection (for example, clicking the year to change it instantly) and also support manual date entry in mm/dd/yyyy format to avoid excessive navigation using arrow buttons. | calender year month picker improvement.webm.webm |  | Jay/Fixed
79 | Contact > Create New Contact | While creating a new contact, the system allows saving without Email But while editing the same contact, the system throws an error: “Email cannot be empty” | Email ID Validation error.mp4 | working | Jay/Fixed
80 | Add Contact | In Contact when we create a new contact there is no specfic conditions for email domain |  | FIXED ON DEV | Bushra/Fixed
81 | Call->Voicemail | The voicemail option in the contacts section is currently not functioning. |  |  | Umar/Fixed
82 | Contact>Contact Validation | In the Contacts tab, users can update the Birth Date under Contact Activity. The date picker should allow selecting the year and month directly and also support manual date entry. | contact activity.png | fixed on dev | Umar/Fixed
83 | email validation | In Contacts, when creating a new contact, there are no restrictions on the email domain. For example, an email like aaaaaaa@aaaa can still be saved. |  | FIXED ON DEV | Jay/Fixed
K) DID Numbers
Added inventory numbers shall have their available features(sms/calls in/out)
While purchasing the DID, user shall see those features before billing parts.
58 | Billing -> Plan | Billing → Plan → DID(s) tab, the cost of purchased DIDs is not displayed. | DID cost.mp4 | done | New purchased DIDs cost showing already purchased DIDs cost not showing
83 | Admin -> number -> add Number | When purchasing the DID, in the payment modal dialog, click on the Pay button and then click on the side screen. The modal dialog closes. then return clicking on the Pay button again and making the payment, repeating this process multiple times results in the same DID being purchased multiple times. | Same DID Purchased Multiple Times .mp4 | done | Umar/Fixed
84 | Admin -> number -> All Number | In dialer DID update shows success toast but throws backend aggregation error when DID is already assigned |  |  | Saurabh/Fixed
85 | Admin -> number -> All Number | I’m getting an error while assigning DID numbers. For +1 812 202 4154, it says “DID number is already assigned” even though it’s not assigned to anyone. Also, +1 812 545 4611 is showing twice—one is already assigned, and the other appears assignable, but when I try to assign it, I get the same error. | DID Number Issue.mp4 | cant find this issue yet | Saurabh/Fixed
L) Calender
86 | Calendar event | when create a event in calendar and delete it from the calendar its deleted from the calender but not in the video section upcoming tab. |  | Fixed on dev (backend) | Umar/Fixed
Others
89 | Settings > Basic Info | First name character limit mismatch between UI validation and database constraint | Validation Mismatch and Database error.webm | Fixed on Dev | Umar/Fixed
93 | User Login sessions | The user is being logged out on uncertain time and in any circumstances, such as in a basic scenario, when a user got a call, then upon 1 ring, the session had log out the user profile, thus that user was not able to pick up their incoming call. | could not add any proof, as the logout time is uncertain |  | Saurabh/Fixed
M) Others
| Deleted user visibility | Deleted users must not be visible in any actions, such as i) While starting a new chat or creating/editing team chat. ii) Users/Inventory/departments lists iii) Licence management list iv) DID inventory list(assigned DID will be un-assigned) v) IVR/Call Queues/any Forward to extension actions. vi) Any search bars, if it includes a separate users list.
59 | Password Reset Link Has No Expiration Time v1.2.8 | There is no time limit or expiration for the password reset link, as it remains valid regardless of when it is opened, though once used password reset link, will be expired when the user uses on second time, but it should notify as expired at initial screen after trying to use it second time. |  | Improvement
60 | Knowledge base DB Collision | some companies are having the same knowledge bases created on a single company, this means all knowledge base records are being unified in several companies:
61 | Login OTP | There should be an OTP attempt limit, for example: if the user is not able to insert otp correctly for 5 times |  | Improvement
62 | Login OTP | There is no otp expiration rule, such as after 10-15 mins the otp shall expire. |  | Improvement | Invalid OTP notification is shown instead of an Expired OTP notification.
63 | User owned DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin |  | Improvement
64 | Overall UI responsiveness | When the user/admin does any change for another user, such as changing their role, creating a department or team chat and adding a scheduling and inviting other users/members, etc. The bug is that the application is not implementing real-time data updates and relies on manual page refreshes, which is an issue with frontend or backend communication, possibly a missing or improperly configured WebSocket connection, incorrect event handling, or issues with a live-reloading development server. The UI needs a mechanism like WebSockets or AJAX calls to listen for server-sent events and update the display dynamically, rather than waiting for the user to manually refresh
65 | Error 404 | Sometimes the Error 404 occurs on some accounts, on which upon clicking "Go To Homepage", The button does not redirect and refresh up on homepage | ClickOnHomepageRedirectionErr404.mp4 | fixed on dev | Could not have that scenario yet.
66 |  | all users except admin, are able to login and use all functions(excluding billing related).
N) Integration
95 | Integration Section | We are not able to connect the hubspot account with the UCaaS application. | CRMIntegrationAndUIResponsiveness.mp4 | Done | Saurabh/ Fixed
96 | Hubspot configuration | On the hubspot configuration, submit button is not working after doing any changes and not even giving a popup. | Hubspot_Submission_Issue.mp4 | Done | Saurabh/ Fixed
97 | When the user tries to connect CRM Integrations | The Ui gets unstable as shown in the Video record. | CRMIntegrationAndUIResponsiveness.mp4 | Done | Saurabh/ Fixed
Reports
102 | Calls Reports | While doing incoming calls the reports are appearing three times for one calls. |  |  | Anusha/Fixed
AI Tools
| Knowledge base | Knowledge base cannot be created by the URL again within a company.
71 | Chatbot Appearance | Chatbot configurations will be just like Tildesk
72 | AI Settings- change AI models | Also need to add and test all models from openal, to get the best one.
73 | Knowledge base | Knowledge base should be added below system prompt for voice agent separately.
74 | AI Receptionist | AI receptionists agent refinement just as vapi, gpt 4.o mini cluster, gpt realtime and realtime-mini
75 | AI Receptionist | Response latency must be more refined/reduced from AI Receptionist
76 | Chatbot Appearance | Still not developed as discussed in meeting.
77 |  | AI agent names must be unique inside a company.
78 |  | Chatbot/Voice agent history must be there unless the admin deletes it.
79 |  | Each AI agent message must have their names whichever are assigned to any platforms(including AI assistant).
80 |  | AI agents list must have platform names on which they're assigned, also designation as AI assistant or AI chatbot.
81 |  | Rename tabs in AI agents creation as AI Voice Receptionist and AI Chatbot.
82 |  | AI agents created with default templates are not visible in domain widget creation.
84 | AI Assistant | We need AI assistant on UCaaS chats also, which will not be customer centric, it will be support centric AI assistant.
85 | AI Settings- change AI models | We need all openai models for ai agent tests.
86 | Admin -> AI Tools -> Agent | Inside the Admin section, under AI Tools, I am able to create a knowledge base successfully. I am also able to create it inside the Agent. However, when it comes to selecting the knowledge base, the scroll button does not go down. I have to zoom out, and only then does it show the knowledge base that I created. | UI Scrolling Error.mp4.mp4 | fixed on dev | Umar/Fixed

## Reports section
No. | Elements/Components | Issues | Screenshots/videorec URLs | Capanicus comments | MCM Comments
1 | call & sms | Call and SMS report search bar is not working | Reports_SearchBarAndFilterErr | api is not giving proper responses | Can you please suggest any solutions we can implement?
2 | Filter in Call Logs | As per the newly added call statuses are not changed in the filter, also the filter itself is not working, and the overall flow of the filter seems dummy and improper.
3 | SMS-logs | SMS-Logs does not consist filter function |  |  | Fixed.But its not working
4 | SMS-logs | In sms report DiD number is not shown in some records
5 | Activity | The activity report is not displaying correctly. Login and logout times are showing as the same.
6 | SMS-Logs | The SMS search filter is not working.
7 | Call Reports | During transfer or conference calls, the report displays “Unknown Contact” and shows the member’s extension number as “Unknown” instead of the correct details.
8 | SMS-Logs | In the SMS log, some data is missing, and the records are not displayed in the correct date order.
9 | Outbound | The outbound report should only show outbound calls, but right now it is also showing inbound calls
10 | Outbound ,Inbound , Call Recording | The contact name/number search filter is not working in Outbound, Inbound, and Call Recording sections.
11 | Inbound Reports | In the Inbound report, the total duration in seconds is incorrect.
12 | Call Reports | When selecting the “Last 7 Days” filter, the report is showing data for 8 days instead of 7 days.
13 | Call Recording | In Call Recording, the “Missed” filter is not working properly.
14 | SMS-Logs | In SMS Log, message reports are being duplicated.

## Android
no | Elements/Components | Issues | Screenshots/videorec URLs | Capanicus comments | MCM Comments
A) Home
1 | Home>Dashboard | In the Home Dashboard, the Outgoing graph is incorrectly including incoming ,voicemail, missed calls counts.
2 | Home -> Admin controls | Call forwarding is not functioning. If we set any value (such as forwarding to an external number) and click Save Changes, the values are not saved. Also on UI, the user is able to forward calls on its own extension.
3 | voicemail setting | Voicemail is not working. Even after enabling voicemail and setting an email address, the calls are not being forwarded to voicemail. Also the connect to voicemail does not work or unclarified.
4 | Home | There is currently no option in the UCaaS application to view the account balance.
5 | Profile | First, there is no option in the application to delete the profile picture, and there are synchronization issues between the web and the application. While the profile picture syncs correctly when uploaded, deleting it requires logging out and then logging back into the application for the change to take effect. Also the user cannot remove that profile photo from web app. and upon Logging into others account, the same profile photo will be set on android app.
B) Phone
6 | Home>Extension Calls | During extension calls, when the user clicks on the transfer option, a number search bar appears. Currently, typing any number in this bar can transfer the call to an external number. However, the transfer feature should only allow searching for and selecting extension numbers or user names within the system,
7 | Phone calls > Filter | In the phone call section, the filter options are not working as follows: This Week Last 7 Days This Month Last 30 Days Last Month
8 | Phone calls > All | In the phone call section, there is a small area with a search bar where All, Incoming, Outgoing, and Missed calls are shown. All these sections should remain, but there is no need to have a search bar there. | Search Bar.jpg |  | Anusha/Fixed
7 | Phone calls | On the contact dial screen, clicking anywhere starts the call, whereas the call should start only by clicking the phone icon on the right corner or by swiping right. |  |  | Fixed
8 | Dialer | When I copy a phone number and paste it with the +91 country code, the system automatically changes it to the USA country code +1. |  |  | Fixed
9 | Dialer | There should be a proper flow for outbound calls, including connecting, calling, and ringing.
10 | Dialer | In the dialpad, when we write a number and place the cursor between digits, any new digit entered should be inserted at the cursor position. However, in the UCaaS application, the digit is always added at the end instead of where the cursor is placed. |  |  | Fixed
11 | Dialer | in dialer if user clicks on the dial button multiple time the call are going 2x or more times. |  |  | Fixed
10 | Dialer | The caller’s phone is ringing, but the agent’s phone still shows “calling".
11 | Dialer | if call Recipient declines the extension call but it keeps ringing on the caller side until the ring timeout ends, and then it stops.
14 | Call logs | There is no information about call duration in the UCaaS phone section. |  |  | Fixed
12 | Home > User | During extension calls, the call disconnects for both parties when transferring the call.
13 | Home > User | During an extension call, when transferring UI, the search bar appears but the user’s name or number does not show up after searching. |  |  | Anusha/Fixed
C) Inbox
14 | inbox | The search functionality does not Exist.
15 | inbox | Actual SMS charges are not showing during the SMS, nor after the SMS is completed. |  |  | Anusha/Fixed
D) Video
19 | Schedule Video Meeting | 1. When we schedule a meeting in that meeting topic there is no character limitations. 2. There is no limitations in password while scheduling a meeting . |  | Fixed | Umar/Fixed
16 | Past Meetings | In past meetings, clicking on attendees does not show the user information.
17 | Feedback | The feedback option does not exist
18 | Invite Members | In Invite Members, once members are selected and you navigate away and return, the selected members are not shown as checked, even though they are still selected.
19 | Video Meeting | When starting a recording, a popup appears saying "Failed to start," but the recording actually begins after clicking OK. Similarly, when stopping the recording, a popup shows "Participant left."
20 | Video Meeting | When an Android user joins a meeting as a guest, and host is a web user if the host tries to turn off the Android user’s camera access, it does not work.
21 | Video Meeting | When a web user creates a meeting and invites an Android user, the Android user joins the meeting. If the Android user clicks the End button, the End for All option appears, and clicking it the meeting ends for all participants, including the host. |  | Fixed | Umar/Fixed
22 | Video Meeting | After scheduling the meeting, when we go to the message info section, the icon that shows how many people have been invited is not working. The icon is not clickable at all. |  | Fixed | Umar/Fixed
21 | Video Meeting | If a meeting is scheduled with a password, all meeting details are shown later, but the set password is not displayed.
24 | Video Meeting | In the video call section, when I start a video call with a user, the invitation is sent,but when the user joins the call, it keeps loading for a long time. Also, during the video call, the number of participants and the option to add participants are not visible. | invitation user joins call participants.mp4 | During the video call, the number of participants and the option to add participants are not visible. :Done | Umar/fixed
22 | Video Meeting | In the video call section the features are missing: 1. Recording 2. Screen Sharing 3. Reaction options 4. Chat feature 5. Info option (with share invite link) 6. Participants and host accesses 7. Background effects 8. Presentation mode 9. invite other users via email | video call missing feature .mp4 | 1.Chat Feature Done 2.Reaction option Done 3.Info(Invite) option Done 4.Participants Done 5.Recording Feature Done 6.Screen share 7.invite other users via email(Add)Done | Given points are added. but screen share is not working.
26 | Video Meeting | While scheduling a meeting, there should be an eye icon to show or hide the password, and there is no option to copy the set password |  | Fixed | Umar/fixed
23 | Video Meeting | There is a screen size/layout issue in meetings. When a user joins with a web participant, the web user’s video does not display properly. same as for screen share UI. | VideoMeetingWebCamView.jpg | Please share screen shot | Image added
24 | Video Meeting | When trying to join a meeting using a pasted link, an error appears: “Meeting does not exist.” | Join meeting using pested Link.mp4 |  | Anusha/Fixed
30 | Video Meeting | When someone schedules a meeting and invites an Android user, the Android app incorrectly shows options to edit or delete the meeting scheduled by another person. |  | Fixed | Umar/Fixed
25 | Video Meeting | In Instant Video Meeting, If the android user tries to connect with web user, by starting a instant meeting and upon inviting the web user from the meeting, that web user gets the meeting invite, but cannot enter in meeting and user gets stuck on scheduled message. | invited meeting scheduled message.mp4 |  | Anusha/Fixed
E) Chat
26 | Start Call | In the Start Call feature, the mute option is not visible, so the user cannot see whether they are muted or unmuted.
27 | Call Duration | The call duration is shown as 0:00, and the actual duration is not being recorded.
28 | Folder>Files | When clicking multiple times to add files, the same file gets added to the folder multiple times.
29 | Emoji | In the Chat section, only a limited number of emojis are visible.
30 | Edit Message | In the Chat section, even older messages can be edited.
31 | Start Call | Even when a user is offline, the “Start Call” option is shown. It should instead display “User Unavailable.”
32 | Direct Message | When clicking on Direct Message and searching by member, the member names do not appear in the dropdown.
33 | Chats | When I delete a folder and notes that I created in the chat section, it does not show the name of the folder and notes that is being deleted. | Folder & Notes Error.mp4
34 | Chats | When an Android user deletes a team chat, it is removed from both the Android app and the web app. However, the user is not removed from the group—only the team chat is deleted. The user still appears in the group, and if any user calls this deleted group, the call still rings. |  |  | Fixed .But the member left the group notification didnt camed .
35 | Chats | Whenever a user sends a message to another user, a notification should appear on the screen. |  | Fixed | Notification working, but upon clicking on chat message. user does not redirect to the specific chat, and mark as read is also not working.
36 | Chats | In the chat section, users cannot delete messages by; they selecting all can only delete messages one at a time
37 | Chats | In the chat section, when one user sends a file, the chat messages keep loading, and the document takes time to open | chat section file send in loding.mp4
38 | Chats | In the chat section the features are missing on the user chat side: • Remove option • Read and Mark option | chat section missing the feature.mp4
39 | Chats | Same as web app, if other member/other user deletes a message, still the user will be able to see on the chat preview
40 | Chats | When replying with a document (such as an image or any other file), the document is not shown in the replied chat.
41 | Chat Creation/Folder | 1. There is no character limit on title in team chat creation/edit, please refer to other apps to understand the logic. 2. There is no character limit on note and folder names. |  |  | Anusha/Fixed
42 | Chats | In the chat section, forwarded messages cannot be selected for multiple users they can only forwarded one at time. | forwarded messages cannot be selected for multiple users.mp4 |  | Anusha/Fixed
43 | Chats | While scrolling, if the user stops and then scrolls again, the UI does not allow to do so, unless the user click and scroll through the messages in the Inchat UI. |  | Fixed | Umar/Fixed
44 | Chats | Sent chat messages are not visible on the chat screen unless we scroll down |  | Fixed | Umar/Fixed
45 | Chats | In the chat, when a user creates a folder and adds a file or image to it, then deletes that file or image from the chat, the file or image is not deleted from the folder — it still appears there. Additionally, the user can add the same deleted file or image to the folder again. |  |  | Anusha/Fixed
F) Others
46 | Initial Permissions Access Request | The app should directly ask for permissions like camera access, sms access, etc. on start of the application and there should be an optional prompt to ignore some unnecessary permissions as "do not ask again", unless the user tries to access those functions on which the system needs those accesses (such as camera, nearby devices, location, media, etc).
47 | OTP Popup | The OTP Pop-up UI is not well structured, it needs minor UI fixes. |  | Improved Design | Umar/Fixed
48 | Login Page | 1. the useremail and password input fields should display the email starting from the very beginning of the field. The left padding should be set to 0, 2. there should be a backspace (<-) icon at the end of the input field. When the cross icon is clicked, all the entered text should be cleared. |  | Fixed | Umar/fixed
Contact
49 | Contact >Birth Date | When creating a contact, the birth date and email field is not shown as mandatory, but it appears as required when updating the contact. |  |  | Anusha/Fixed
50 | Contact >Birth Date | In the contact section, the birth date field only allows selecting today’s date.
51 | Contact | In the Contact section, the chat icon is displayed instead of the SMS icon.
52 | Contact | In the Contact section, the “Created By” and “Updated By” information is not visible.
53 | Contact>Activity Logs | In the Contact section, the activity logs are not showing any information.
54 | Contact>SMS | When sending an SMS through the Contact section, the country code is predefined as +1. If the number already includes the country code, it gets added again, resulting in two country codes.
55 | Contact>Edit Contact | When editing a contact, the gender field is not being updated.
56

## IOS
no | Elements/Components | Issues | Screenshots/videorec URLs
A) Home
1 | Home -> Admin controls | Call forwarding is not functioning completely. If we set any value (such as forwarding to an external number) and click Save Changes, the values are not saved. Also on UI, the user is able to forward calls on its own extension.
2 | voicemail setting | Voicemail is not working. Even after enabling voicemail and setting an email address, the calls are not being forwarded to voicemail. Also the connect to voicemail does not work or unclarified.
3 | Home | There is currently no option in the UCaaS application to view the account balance.
4 | Profile | First, there is no option in the application to delete the profile picture, and there are synchronization issues between the web and the application. While the profile picture syncs correctly when uploaded, deleting it requires logging out and then logging back into the application for the change to take effect. Also the user cannot remove that profile photo from web app. and upon Logging into others account, the same profile photo will be set on IOS app.
B) Phone
5 | Phone calls > Filter | In the phone call section, the filter options are not working as follows: This Week Last 7 Days This Month Last 30 Days Last Month
6 | Phone calls > All | In the phone call section, there is a small area with a search bar where All, Incoming, Outgoing, and Missed calls are shown. All these sections should remain, but there is no need to have a search bar there. | Search Bar.jpg
7 | Phone calls | On the contact dial screen, clicking anywhere starts the call, whereas the call should start only by clicking the phone icon on the right corner or by swiping right.
8 | Dialer | When I copy a phone number and paste it with the +91 country code, the system automatically changes it to the USA country code +1.
9 | Dialer | There should be a proper flow for outbound calls, including connecting, calling, and ringing.
10 | Dialer | In the dialpad, when we write a number and place the cursor between digits, any new digit entered should be inserted at the cursor position. However, in the UCaaS application, the digit is always added at the end instead of where the cursor is placed.
11 | Dialer | in dialer if user clicks on the dial button multiple time the call are going 2x or more times.
12 | Dialer | The caller’s phone is ringing, but the agent’s phone still shows “calling".
13 | Dialer | if call Recipient declines the extension call but it keeps ringing on the caller side until the ring timeout ends, and then it stops.
14 | Call logs | There is no information about call duration in the UCaaS phone section.
15 | Home > User | During an extension call, when transferring UI, the search bar appears but the user’s name or number does not show up after searching.
16 | Home > User | During extension calls, the call disconnects for both parties when transferring the call.
C) Inbox
17 | inbox | The search functionality in the does not work.
18 | inbox | Actual SMS charges are not showing during the SMS, nor after the SMS is completed.
D) Video
19 | Schedule Video Meeting | 1. When we schedule a meeting in that meeting topic there is no character limitations. 2. There is no limitations in password while scheduling a meeting . |  | Fixed
20 | Video Meeting | When an IOS user joins a meeting as a guest, and host is a web user if the host tries to turn off the IOS user’s camera access, it does not work.
21 | Video Meeting | When a web user creates a meeting and invites an IOS user, the IOS user joins the meeting. If the IOS user clicks the End button, the End for All option appears, and clicking it the meeting ends for all participants, including the host. |  | Fixed
22 | Video Meeting | After scheduling the meeting, when we go to the message info section, the icon that shows how many people have been invited is not working. The icon is not clickable at all. |  | Fixed
23 | Video Meeting | If a meeting is scheduled with a password, all meeting details are shown later, but the set password is not displayed.
24 | Video Meeting | In the video call section, when I start a video call with a user, the invitation is sent,but when the user joins the call, it keeps loading for a long time. Also, during the video call, the number of participants and the option to add participants are not visible. | invitation user joins call participants.mp4 | During the video call, the number of participants and the option to add participants are not visible. :Done
25 | Video Meeting | In the video call section the features are missing: 1. Recording 2. Screen Sharing 3. Reaction options 4. Chat feature 5. Info option (with share invite link) 6. Participants and host accesses 7. Background effects 8. Presentation mode 9. invite other users via email | video call missing feature .mp4 | 1.Chat Feature Done 2.Reaction option Done 3.Info(Invite) option Done 4.Participants Done 5.Recording Feature Done 6.Screen share 7.invite other users via email(Add)Done
26 | Video Meeting | While scheduling a meeting, there should be an eye icon to show or hide the password, and there is no option to copy the set password |  | Fixed
27 | Video Meeting | In Instant Video Meeting, If the IOS user tries to connect with web user, by starting a instant meeting and upon inviting the web user from the meeting, that web user gets the meeting invite, but cannot enter in meeting and user gets stuck on scheduled message. | invited meeting scheduled message.mp4
28 | Video Meeting | There is a screen size/layout issue in meetings. When a user joins with a web participant, the web user’s video does not display properly. same as for screen share UI. |  | Please share screen shot
29 | Video Meeting | When trying to join a meeting using a pasted link, an error appears: “Meeting does not exist.” | Join meeting using pested Link.mp4
30 | Video Meeting | When someone schedules a meeting and invites an IOS user, the IOS app incorrectly shows options to edit or delete the meeting scheduled by another person. |  | Fixed
E) Chat
31 | Chat Creation/Folder | 1. There is no character limit on title in team chat creation/edit, please refer to other apps to understand the logic. 2. There is no character limit on note and folder names.
32 | Chats | When I delete a folder and notes that I created in the chat section, it does not show the name of the folder and notes that is being deleted. | Folder & Notes Error.mp4
33 | Chats | When an IOS user deletes a team chat, it is removed from both the IOS app and the web app. However, the user is not removed from the group—only the team chat is deleted. The user still appears in the group, and if any user calls this deleted group, the call still rings.
34 | Chats | Whenever a user sends a message to another user, a notification should appear on the screen. |  | Fixed
35 | Chats | In the chat section, forwarded messages cannot be selected for multiple users they can only forwarded one at time. | forwarded messages cannot be selected for multiple users.mp4
36 | Chats | In the chat section, users cannot delete messages by; they selecting all can only delete messages one at a time
37 | Chats | In the chat section, when one user sends a file, the chat messages keep loading, and the document takes time to open | chat section file send in loding.mp4
38 | Chats | In the chat section the features are missing on the user chat side: • Remove option • Read and Mark option | chat section missing the feature.mp4
39 | Chats | Same as web app, if other member/other user deletes a message, still the user will be able to see on the chat preview
40 | Chats | While scrolling, if the user stops and then scrolls again, the UI does not allow to do so, unless the user click and scroll through the messages in the Inchat UI. |  | Fixed
41 | Chats | Sent chat messages are not visible on the chat screen unless we scroll down |  | Fixed
42 | Chats | In the chat, when a user creates a folder and adds a file or image to it, then deletes that file or image from the chat, the file or image is not deleted from the folder — it still appears there. Additionally, the user can add the same deleted file or image to the folder again.
43 | Chats | When replying with a document (such as an image or any other file), the document is not shown in the replied chat.
F) Others
44 | Login Page | 1. the useremail and password input fields should display the email starting from the very beginning of the field. The left padding should be set to 0, 2. there should be a backspace (<-) icon at the end of the input field. When the cross icon is clicked, all the entered text should be cleared. |  | Fixed
45 | Initial Permissions Access Request | The app should directly ask for permissions like camera access, sms access, etc. on start of the application and there should be an optional prompt to ignore some unnecessary permissions as "do not ask again", unless the user tries to access those functions on which the system needs those accesses (such as camera, nearby devices, location, media, etc).
46 | OTP Popup | The OTP Pop-up UI is not well structured, it needs minor UI fixes. |  | Improved Design

## Super-Admin
no | Elements/Components | Issues | Screenshots/videorec URLs | developer response | MCM Comments
1 | SMS History | The cost, charge, and profit are not showing. |  |  | Umar/Fixed
2 | Video Meetings | In Video Meeting → Search Filter, when selecting the Scheduled type, no results are displayed even though meetings exist.
3 | Company -> Users | create the user and select the other roles but, the created user’s role is displayed as Admin in the UCaaS application. |  | need to discuss ... from where you changed the role?
4 | Company -> Users | New created user is not assigned to the already purchased license, and the created user is not shown in the Billing Licenses section. |  | need to discuss
5 | Company -> Users | When added a user from Super Admin and logs in this created user, only the Home, Phone, and Admin sections are visible after login. |  | need to discuss ... do you want to show all?
6 | Rate Card | When adding a rate card with an existing name, an error message is shown. However, while editing a rate card and entering an existing name the ratecard name updated successfully with same name. |  | Done | Umar/Fixed
7 | Rate Card -> Add Rate | When uploading the .xlsx file, the error ‘Data format issue’ is shown. |  | done | Umar/Fixed
8 | Companies | When Search any company in the search result the company plan name is not showing.
9 | Rate Card -> Rate Card Details | Searching is not working in the Rates table and shows the error: ‘search is not allowed.’ |  | done | Umar/Fixed
10 | Rate Card -> Rate Card Details | Pagination page-size selector UI issue: When clicking on the page-size dropdown, the dropdown values appear behind the table and are not visible. |  | done | Dropdown is showing but Its not working
11 | Rate Card -> Rate Card Details | When trying to add a new rate in the added rates, the error message ‘UUID is a required field’ appears. |  | done | Umar/Fixed
12 | Company -> Virtual Number and Calls | Pagination page-size selector UI issue: When clicking on the page-size dropdown, the dropdown values appear behind the table and are not visible. | Pagination UI Issue.mp4 | video and description are not same ( working on both cases) | Umar/Fixed
13 | Company -> Sites | If we try to delete a created site, the error message ‘Something went wrong’ is shown, and the site is not deleted.” |  | done | Umar/Fixed
14 | Plan | When creating a new plan, the Save button does not work after filling all details. Similarly, when editing a plan, the Update Feature button does not work. |  | done | Umar/Fixed
15 | Companies-> Total Sites | When a new company is created in UCaaS, the Total Sites count increases in the Super Admin → Companies section. However, after deleting the company in UCaaS, the Total Sites count does not decrease accordingly. |  | done | Umar/Fixed
16 | Companies profile -> Virtual Number | In the Virtual Number section, some DID numbers are showing the wrong type. For example, in UCaaS, a number is shown as Mobile, but in the Super Admin dashboard, it appears as Toll-free. |  | done | Umar/Fixed
17 | Companies profile -> Virtual Number | In the ‘Assign to’ column, the assigned DID username is not displayed; instead, it shows ‘None’. | Assigned DID username.png | done | Umar/Fixed
18 | Companies-> Licenses | The used license count in the Licenses column is incorrect. Downgraded or revoked licenses are not subtracted from the used count, even though the revoked number is displayed correctly. | Companies Licenses count.mp4 | done | Umar/Fixed
19 | UCaaS Super-Admin https://admin-ucaas.mycountrymobile.com/ | In the Super-Admin UI, the admin is not able to make a user's account deactivate or expire, upon using on these functions, those user will be logged out only. and after logging in again, it will fetch some errors, but can still work with their account. | Super-Admin-UCaaS-UserActivateDeactivateExpireErr.mkv | need discussion
20 | UCaaS Super-Admin - DID numbers https://admin-ucaas.mycountrymobile.com/ | If the Super-Admn deletes a user's DID number, it does not get deleted from the user account, and still the user is able to use that DID number. | SuperAdmin-DeleteUserDIDNumber.mp4 | tau will check
21 | The Company->admin Login | The Super admin is not able login with the given company's admin login option | Super-Admin-UCaaS-UserActivateDeactivateExpireErr.mkv | need discussion
22 | Company dashboard | The yearly meeting graph is not showing any report, even though the company had their meeting history. | Super-Admin-Dashboard_Yearly_meeting_report.mp4 | working
23 | User's own DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin |  | need discussion

## All Pendding IssuesImprovement
| Elements/Components | Issues | Screenshots/videorec URLs | Capanicus comments | MCM Comments
Web
A. Phone
1 | call transfer to extension | When a call is made from the UCaaS web to a non-UCaaS number and then transferred to another UCaaS extension, the call connects successfully. Charges are deducted for the first user’s call log and charges are correct, but charges for the second user (extension transferred call recipient) are not shown in the call-log report. |  | Testing | Umar - Pending
2 | transfer call report on external number | When the user transfers the call to an external number, the call duration and cost is not being considered on the master caller's call report. |  |  | Anusha - Pending
3 | Call Merge | The MasterCaller stucks at call when all other recipiants are left. |  | when master caller hang then all other hang , if master call not hang he will still be able to add more calls | We need to discuss this with furqan sir.
4 | Dialer search bar | The user should be able to search saved contacts on the dialer, including users with their extension and contact number(which is added in user details). |  |  | Saurabh - Pending
5 | Recordings Charge | Need to implement call recordings charge on companies user base capping, and storage should be allotted differently |  | Improvement | Saurabh - Pending
6 | Profile-> incoming calls -> Forward Calls | Play Announcement is not working in User Profile of Phone tab. |  | Testing | Jay - Pending
7 | Sentiment Analysis | The Sentiment analysis is not working as expected. |  |  | Saurabh - Pending
8 | Voicemail Timeout issue | The voicemail stays longer than 30 seconds. |  |  | Bhushra - Pending
9 | Decline with message | On Inbound calls, Decline with message is not working, SMS cost prompt and DLC required(if needed) restriction shall be shown to the user. |  |  | Saurabh - Pending
10 | Free Call Minutes | Call charges are being deducted even after the free call minutes are finished. |  |  | Saurabh - Pending
11 | Call Recording Deletion | if the recording storage is free, we'll delete all recordings after 7 days after notifying the user before certain time. |  | Improvement
12 | transfer calls | when the user does an extension call and then the same caller transfers the extension call to another extension, all calls will be disconnected immediately. |  |  | shailendra - pending
13 | monitoring | In the Monitoring section, most features are not functioning correctly. Only Listen and Barge are available, and within Barge, functions like Mute, Transcripts, Hold, and others don’t work. The Campaign section shows no reports, and even when a campaign is opened, it still displays Monitoring – Call Queue at the top. Overall, the sections are not working properly. |  |  | shailendra - pending
14 | Transcription | System does not keep transcription on when user close the Call UI and get back to transcription. |  |  | saima - pending
15 | Transcription in Hindi | Transcription in Hindi is not working now |  |  | Saurabh - Pending
16 | Call Monitoring | Except All Calls, All other call monitoring tabs are not working, also call queue waiting callers records are being stuck on tab |  |  | Saurabh - Pending
B. Chat
17 | Chat Delete access | If the user does not have access to delete, the user still can delete chats via team, favorites and direct tab | detele all chat.mp4 | FIXED ON DEV | Umar/Fixed
18 | Chat Reload Issue | sometimes the user cannot see previous messages and even previous does not reload automatically until the user refreshes the page |  |  | Anusha/Fixed
19 | Chat Reload and Jump to Bottom | To stabilize the feed, implement a top-loading spinner combined with CSS overflow-anchor: auto to prevent the view from jumping when older messages prepend. Additionally, add a floating "down-arrow" button that appears when the user scrolls up, providing a one-click shortcut to return to the latest message. | https://capanicus.slack.com/files/U09S8RH17J5/F0AAKHXP71Q/chatloadingandjumptobottom.png |  | Anusha/Fixed
20 | Click on Created folder | If the user clicks on created chat folder name via vague notification, then gets back on chat, the user will be redirected to the top of the chat. |  |  | Anusha/Fixed
21 | Chat> Click on Replied Message | Sometimes, when clicking on a reply message, it does not redirect to original message and instead shows the notification: ‘Original message not found. It might be in an older conversation.’ |  | FIXED ON DEV | Anusha/Fixed
22 | Chat>message | When typing a long message in the chat input field, pressing Shift + Ctrl to move to a new line instead moves the cursor directly to the bottom line. |  |  | shailendra -Not fixed
23 | chat->emoji | There are some categories of emojis are missing, e.g., flags, |  | improvement | shailendra - pending
24 | chat->folder | There is no character limit on note and folder names. |  | FIXED ON DEV | Anusha/Fixed
25 | Chat AI Assistant | A chat AI assistant shall be included for user's quick & easy issue resolution as per the FIgma design given in "Screenshots/videorec URLs" column |  |  | shailendra - pending
26 | Join Call Button | Join button which was removed, is still pending to connect ongoing team chat call. |  |  | Umar/Fixed
27 | Chat Section | A member cannot ping/tag other members on team chat (for example, @admin) |  |  | shailendra - pending
28 | chat | the change group photo not available after creating a group. |  |  | shailendra - pending
29 | Chat | While editing a message draft in one chat, switching to a different chat carries the same edited draft into the other chat. When the draft is sent, it is delivered to the original chat instead of the currently active chat. | recording.webm |  | Umar/Fixed
30 | Chat > adding notes | Formatting option labels are visible for a few milliseconds before the notes editor loads properly. | UI flicker in notes.webm IMAGE: UI notes lable name shows while it is loading .png |  | Jay - Pending
31 | Chat > NOTES | Deleted note activity redirects to notes instead of showing deleted state. Also group or team does not shows as it is whether the team name is in UPPERCASE or lowecase style | Team or group Name does not shows as it is written uppercase and lowecase and second notes after deletion, edited.mp4 |  | Jay- Pending
32 | Team Chat> removed/left user | In a team group, if any user is removed or leaves the group, their name and profile avatar are not shown in their previous chat messages. | Removed/left user chat message issue.mp4 |  | Umar/Fixed
33 | Reply chat | When replying to a message in one user’s chat and then opening another user’s chat, the typed reply message appears in the other user’s chat. | Reply message issue.mp4 |  | Umar/Fixed
C. Video Meeting
34 | Join Meeting Via Link | If an unknown user joins the meeting via the URL link and enters only spaces in the Name field, the user is still able to join the meeting. |  |  | Umar/Fixed
35 | video - recording | When I click the recording icon during a meeting, it loads and starts recording, but the recording info—like how long it has been recording—doesn’t show. |  |  | Pending/Bushra
36 | Video Improvement Part | Suppose I scheduled a meeting for one hour later and switch to another tab to work. When the meeting time arrives, I should receive a system notification. However, no system notification is received. |  | improvement | Pending/Bushra
37 | join buttton in notification secction | Add a "Join" button in the notification section to directly join a meeting when invited.
38 | join meeting multiple time | A user can join the same meeting multiple times from different tabs using the same ID and name, which is not expected behavior and should be fixed. 1. There is no user validation on checking if the user is already on a video call. |  |  | Pending/ Bushra
39 | Video Improvement Part | Suppose I have scheduled a meeting for one hour later, and due to some work I am using another tab, then I should receive a system notification saying that the meeting time has arrived. |  | improvement | Pending/ Bushra
40 | Video Meeting | A user can join the same meeting multiple times from different tabs using the same ID and name, which is not expected behavior and should be fixed. | recording.webm |  | Pending/ Bushra
E. Home
41 | Campaign Dashboard | In the campaign dashboard, the agent report displays the wrong count of campaigns assigned to agents.
F. User Settings
42 | Settings - Video | When we set profile photo from android, on the web version, the user won't be able to remove that profile photo
G. Admin Section
43 | Call Queues Creation | The custom made user role can't be the manager of a Call Queues, despite giving all permissions to that user role |  | discussed with raman
44 | admin - sms/calling rates | In Admin Settings → SMS/Calling Rates, only Outbound Rates are shown, without clearly indicating whether they are for SMS or calling. After selecting a country, landline and mobile rates appear, but SMS or calling is still not specified. Also, searching for Canada shows two landline rates. |  | need to discuss
45 | IVR Function | The overall IVR UI is not user friendly and does not seem professional and has some Logical bugs, the media function development is not completely implemented, where the user should have features to make the text to speech audio in multiple voices and accents, sample designs are given in "Screenshots/videorec URLs" column | Sample image 1.jpeg Sample image 2.jpeg
46 | IVR Function | The Generic Key press function does not work on IVR calls, such as if the IVR is set on pressing * to go back on previous menu and # to repeat the present menu, also there is not option for 0 digit keypress | IVR Previous and Repeat Manue.mp4
47 | User ID | multiple systems with a single user ID can call different users without knowing each other.
I. Campaign
48 | Dialed Numbers | After running the campaigns the connected calls number is not visible |  | (Working fine with not anwered), Unable to check answered (webhook issue) | Anusha/Pending
49 | Campaign >Campain Logs | In campaign call reports, the Notes option appears for certain calls even when the call status is Cancelled. |  |  | Anusha/Pending
50 | Campaigns Reports | In some campaigns the notes are visible even when the call is getted cut
51 | Create Campaign | While creating a campaign in media before submitting the campaign settings when the user changes the dialer the script is removed from it and during the campaign calls the script is empty. | campaign script.webm | add video | Video Added
52 | Campaign>Recording | When an agent does not have recording access at the agent level, call recording does not work during a campaign, even if recording is enabled in the campaign settings. | Campaign Call recording issue.mp4 | Need clarification | Video Added
I) Inbox
53 | SMS-Search bar | The search bar is not working.
54 | SMS-Search bar | names wth numbers saved in contacts and numbers used on which SMS are sent shall be visible on the search bar including users with their contact number(which is added in user details)..
55 | SMS -> Message | When the sms is sent from report a popup occurs no sufficient balance to send message but by clicking in confirm the message is sent |  |  | Anusha/Fixed
56 | Inbox > SMS | Contact profile picture is not displayed in Inbox conversation list or contacts | Contact profile picture issue.mp4
57 | Inbox > SMS Tab | Add search functionality in Message Inbox to find contacts by name or number |  |  | Umar/partially fixed Its added but not working.
58 | SMS -> Message | Delivery Status Missing: The system does not notify if the SMS is sent, delivered, or failed.UCAAS |  | Is it done from SMS local..? and part of improvement | But that's a mandatory function which other SMS apps provides.
59 | SMS -> Message | In the Inbox, when I try to send a message to any number, a “"available_balance" is not allowed” pop-up appears, and the SMS is not sent. | inbox issue.mp4 | Add video | shailendra - pending
60 | Sms > Plans > Free SMS | Free SMS are not being deducted from given free SMS in plan -> Billing.
J) Contacts
61 | Contacts and Search bar | Users shall be added with their contact numbers and other info (which is added in user details).
K) DID Numbers
62 |  | Added inventory numbers shall have their available features(sms/calls in/out)
63 |  | While purchasing the DID, user shall see those features before billing parts.
64 | Billing -> Plan | Billing → Plan → DID(s) tab, the cost of purchased DIDs is not displayed. | DID cost.mp4 | done | New purchased DIDs cost showing already purchased DIDs cost not showing
M) Others
65 | Deleted user visibility | Deleted users must not be visible in any actions, such as i) While starting a new chat or creating/editing team chat. ii) Users/Inventory/departments lists iii) Licence management list iv) DID inventory list(assigned DID will be un-assigned) v) IVR/Call Queues/any Forward to extension actions. vi) Any search bars, if it includes a separate users list.
66 | Password Reset Link Has No Expiration Time v1.2.8 | There is no time limit or expiration for the password reset link, as it remains valid regardless of when it is opened, though once used password reset link, will be expired when the user uses on second time, but it should notify as expired at initial screen after trying to use it second time. |  | Improvement
67 | Knowledge base DB Collision | some companies are having the same knowledge bases created on a single company, this means all knowledge base records are being unified in several companies:
68 | Login OTP | There should be an OTP attempt limit, for example: if the user is not able to insert otp correctly for 5 times |  | Improvement
69 | Login OTP | There is no otp expiration rule, such as after 10-15 mins the otp shall expire. |  | Improvement
70 | User owned DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin |  | Improvement
71 | Overall UI responsiveness | When the user/admin does any change for another user, such as changing their role, creating a department or team chat and adding a scheduling and inviting other users/members, etc. The bug is that the application is not implementing real-time data updates and relies on manual page refreshes, which is an issue with frontend or backend communication, possibly a missing or improperly configured WebSocket connection, incorrect event handling, or issues with a live-reloading development server. The UI needs a mechanism like WebSockets or AJAX calls to listen for server-sent events and update the display dynamically, rather than waiting for the user to manually refresh
72 | Error 404 | Sometimes the Error 404 occurs on some accounts, on which upon clicking "Go To Homepage", The button does not redirect and refresh up on homepage | ClickOnHomepageRedirectionErr404.mp4 | fixed on dev | Could not have that scenario yet.
73 |  | all users except admin, are able to login and use all functions(excluding billing related).
Android
A) Home
1 | Home>Dashboard | In the Home Dashboard, the Outgoing graph is incorrectly including incoming ,voicemail, missed calls counts.
2 | Home -> Admin controls | Call forwarding is not functioning. If we set any value (such as forwarding to an external number) and click Save Changes, the values are not saved. Also on UI, the user is able to forward calls on its own extension.
3 | voicemail setting | Voicemail is not working. Even after enabling voicemail and setting an email address, the calls are not being forwarded to voicemail. Also the connect to voicemail does not work or unclarified.
4 | Home | There is currently no option in the UCaaS application to view the account balance.
5 | Profile | First, there is no option in the application to delete the profile picture, and there are synchronization issues between the web and the application. While the profile picture syncs correctly when uploaded, deleting it requires logging out and then logging back into the application for the change to take effect. Also the user cannot remove that profile photo from web app. and upon Logging into others account, the same profile photo will be set on android app.
B) Phone
6 | Home>Extension Calls | During extension calls, when the user clicks on the transfer option, a number search bar appears. Currently, typing any number in this bar can transfer the call to an external number. However, the transfer feature should only allow searching for and selecting extension numbers or user names within the system,
7 | Phone calls > Filter | In the phone call section, the filter options are not working as follows: This Week Last 7 Days This Month Last 30 Days Last Month
8 | Dialer | There should be a proper flow for outbound calls, including connecting, calling, and ringing.
9 | Dialer | The caller’s phone is ringing, but the agent’s phone still shows “calling".
10 | Dialer | if call Recipient declines the extension call but it keeps ringing on the caller side until the ring timeout ends, and then it stops.
11 | Home > User | During extension calls, the call disconnects for both parties when transferring the call.
C) Inbox
12 | inbox | The search functionality does not Exist.
D) Video
13 | Past Meetings | In past meetings, clicking on attendees does not show the user information.
14 | Feedback | The feedback option does not exist
15 | Invite Members | In Invite Members, once members are selected and you navigate away and return, the selected members are not shown as checked, even though they are still selected.
19 | Video Meeting | When starting a recording, a popup appears saying "Failed to start," but the recording actually begins after clicking OK. Similarly, when stopping the recording, a popup shows "Participant left."
16 | Video Meeting | When an Android user joins a meeting as a guest, and host is a web user if the host tries to turn off the Android user’s camera access, it does not work.
17 | Video Meeting | If a meeting is scheduled with a password, all meeting details are shown later, but the set password is not displayed.
18 | Video Meeting | In the video call section the features are missing: 1. Recording 2. Screen Sharing 3. Reaction options 4. Chat feature 5. Info option (with share invite link) 6. Participants and host accesses 7. Background effects 8. Presentation mode 9. invite other users via email | video call missing feature .mp4 | 1.Chat Feature Done 2.Reaction option Done 3.Info(Invite) option Done 4.Participants Done 5.Recording Feature Done 6.Screen share 7.invite other users via email(Add)Done | Given points are added. but screen share is not working.
19 | Video Meeting | There is a screen size/layout issue in meetings. When a user joins with a web participant, the web user’s video does not display properly. same as for screen share UI. | VideoMeetingWebCamView.jpg | Please share screen shot | Image added
E) Chat
20 | Start Call | In the Start Call feature, the mute option is not visible, so the user cannot see whether they are muted or unmuted.
21 | Call Duration | The call duration is shown as 0:00, and the actual duration is not being recorded.
22 | Folder>Files | When clicking multiple times to add files, the same file gets added to the folder multiple times.
23 | Emoji | In the Chat section, only a limited number of emojis are visible.
24 | Edit Message | In the Chat section, even older messages can be edited.
25 | Start Call | Even when a user is offline, the “Start Call” option is shown. It should instead display “User Unavailable.”
26 | Direct Message | When clicking on Direct Message and searching by member, the member names do not appear in the dropdown.
27 | Chats | When I delete a folder and notes that I created in the chat section, it does not show the name of the folder and notes that is being deleted. | Folder & Notes Error.mp4
28 | Chats | When an Android user deletes a team chat, it is removed from both the Android app and the web app. However, the user is not removed from the group—only the team chat is deleted. The user still appears in the group, and if any user calls this deleted group, the call still rings. |  |  | Fixed .But the member left the group notification didnt camed .
29 | Chats | Whenever a user sends a message to another user, a notification should appear on the screen. |  | Fixed | Notification working, but upon clicking on chat message. user does not redirect to the specific chat, and mark as read is also not working.
30 | Chats | In the chat section, users cannot delete messages by; they selecting all can only delete messages one at a time
31 | Chats | In the chat section, when one user sends a file, the chat messages keep loading, and the document takes time to open | chat section file send in loding.mp4
32 | Chats | In the chat section the features are missing on the user chat side: • Remove option • Read and Mark option | chat section missing the feature.mp4
33 | Chats | Same as web app, if other member/other user deletes a message, still the user will be able to see on the chat preview
34 | Chats | When replying with a document (such as an image or any other file), the document is not shown in the replied chat.
F) Others
35 | Initial Permissions Access Request | The app should directly ask for permissions like camera access, sms access, etc. on start of the application and there should be an optional prompt to ignore some unnecessary permissions as "do not ask again", unless the user tries to access those functions on which the system needs those accesses (such as camera, nearby devices, location, media, etc).
Contact
36 | Contact >Birth Date | In the contact section, the birth date field only allows selecting today’s date.
37 | Contact | In the Contact section, the chat icon is displayed instead of the SMS icon.
38 | Contact | In the Contact section, the “Created By” and “Updated By” information is not visible.
39 | Contact>Activity Logs | In the Contact section, the activity logs are not showing any information.
40 | Contact>SMS | When sending an SMS through the Contact section, the country code is predefined as +1. If the number already includes the country code, it gets added again, resulting in two country codes.
41 | Contact>Edit Contact | When editing a contact, the gender field is not being updated.
Super Admin
1 | Video Meetings | In Video Meeting → Search Filter, when selecting the Scheduled type, no results are displayed even though meetings exist.
2 | Company -> Users | create the user and select the other roles but, the created user’s role is displayed as Admin in the UCaaS application. |  | need to discuss ... from where you changed the role?
3 | Company -> Users | New created user is not assigned to the already purchased license, and the created user is not shown in the Billing Licenses section. |  | need to discuss
4 | Company -> Users | When added a user from Super Admin and logs in this created user, only the Home, Phone, and Admin sections are visible after login. |  | need to discuss ... do you want to show all?
5 | Companies | When Search any company in the search result the company plan name is not showing.
6 | Rate Card -> Rate Card Details | Pagination page-size selector UI issue: When clicking on the page-size dropdown, the dropdown values appear behind the table and are not visible. |  | done | Not Fixed
7 | UCaaS Super-Admin https://admin-ucaas.mycountrymobile.com/ | In the Super-Admin UI, the admin is not able to make a user's account deactivate or expire, upon using on these functions, those user will be logged out only. and after logging in again, it will fetch some errors, but can still work with their account. | Super-Admin-UCaaS-UserActivateDeactivateExpireErr.mkv | need discussion
8 | UCaaS Super-Admin - DID numbers https://admin-ucaas.mycountrymobile.com/ | If the Super-Admn deletes a user's DID number, it does not get deleted from the user account, and still the user is able to use that DID number. | SuperAdmin-DeleteUserDIDNumber.mp4 | tau will check
9 | The Company->admin Login | The Super admin is not able login with the given company's admin login option | Super-Admin-UCaaS-UserActivateDeactivateExpireErr.mkv | need discussion
10 | Company dashboard | The yearly meeting graph is not showing any report, even though the company had their meeting history. | Super-Admin-Dashboard_Yearly_meeting_report.mp4 | working
11 | User's own DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin |  | need discussion
12 | Scheduled Meeting and event | When any company user schedules or creates an event, the scheduled meeting or event appears in the Video Meeting section of all companies. | Scheduled Meeting and event showing in all companies.mp4
13 | Home Dashboard | Need to rename the 'new company' as 'active company', which is not appearing on the superadmin home dashboard.
14 | Companies-> Profile | When the company name is updated, the changes are not reflected in the company Admin panel, but still it is updated correctly in the Super Admin panel, also the company name is editable with the same name as per the other company.
15 | Companies->Dashboard | The company dashboard graphs are inaccurate and displaying incorrect information.
16 | Companies-> Profile | In the Company Info section, the total number of members and the number of DIDs purchased are not shown properly which seems incorrect.
17 | Companies->Virtual Number | In Companies -> Virtual Numbers section, the number types of purchased/assigned numbers are incorrect.
18 | Companies->Virtual Number ->Filter | In the Companies -> Virtual Numbers section, the “Select DID Type” filter currently shows only two options: Local and Toll-Free. The Mobile type option is missing, and the search bar in the Select Type dropdown is not required and should be removed.
19 | Companies->Video Meetings | In the Upcoming Meetings section, if a user schedules a meeting/event from any company, the records are being shown on all companies.
20 | Companies->Site->Filter | . Companies -> Company(e.g., DemoCompany6) -> Site -> Filter is not working.
21 | Companies->Video Meetings | In the Upcoming Meetings section, the “Select Type” and “Select Status” dropdowns include a search bar, which is not required and should be removed.
22 | Companies->Video Meetings | In the Past Meetings section, when filtering by status “Complete,” an error popup appears saying “Something went wrong.”
23 | Companies->Calls->Filter | In Companies > Calls > Filter > Select Date, when selecting “Last 7 Days,” records from 8 days are being displayed.
24 | Companies->Calls->Filter | In Companies > Calls > Filter, the “Enter Name” search is not working.
25 | Companies->Calls->Filter | In Companies > Calls > Filter > Select Type, “Missed Calls” and “Voicemail” are not visible and are incorrectly listed under “Inbound Calls.”
26 | Companies->Video Meetings | In Video Meetings, the label “Attendees” should be changed to “Invitees.”