## Improvements
Elements/Components | Improvements | Priority | Capanicus comments | MCM Comments
| Also need to make the UI well-responsive for mobile/tablet view. | High
| Home Dashboard, Chat/Inbox, Phone Dialer, Phone Section, Video Meetings, Side Menus, Departments, Admin Section: DID purchase(Sign up), IVR(Text to speech), AI tools UI updates and improvement.png | High
AI Feature: | AI assist in chat dashboard. | High
| Need to create our own AI model with Ollama | High
| AI writer - The chat functions should include chat AI assist for user's quick texting of last question | High
| AI Call Tags - Auto-categorizes calls (e.g., "Billing," "Support") for reporting. | High
| AutoTransfer to real agent in ChatBot. | High
| AI agents sentiment dashboard. | High
| Chat Admin can barge between human agent and customer. | High
| Click to dial on Domain Chatbot widget, in the chat call will transfer active agent | High
| AI receiptionist with scheduled callbacks: should be able book an appointment if the human agent is not available at that time. | High
| Chatbot appearance and Agent test button on domain. | High
| OutBound AI Reception | High
Chat: | Need to add all chats filter which will show overall chats including omnichannel chats with their respected logo/icons, as given in design reference | High
| The user should be able to see Message not Delivered, Delivered and Seen ticks. | High
| A member cannot ping/tag other members on team chat (for example, @admin). | High | Done on Beta | Umar - Fixed on Beta
| In chat, attachment/Image/Video should be visible in small window. | High
| In chats, add the search bar option for searching the previous chats. | High | Done on Beta | Umar - Fixed on Beta
| In the chat section there are no specific options to pin a direct chat or group chat(max should be 3 chats). | High
| If I want to select and forward multiple messages (3–4) at a time, there is no option available to do so, similar to WhatsApp. | High
| Add a “Jump to Latest Message” button(perhaps an icon: DownArrow) in the chat. When the user scrolls away from the bottom, the button appears and allows direct navigation to the most recent message without manual scrolling, similar to WhatsApp. | High | Done on Beta | shailendra - fixed
| In the chat section, features such as contact sharing, polling, audio messages, and event options—similar to WhatsApp—are not available. | High | Audio message is done
| In the Notes/folders view, the creator’s name and creation time should be displayed below or beside each created note/folder title. | High
| Creation messages show the creator and note/folder name, but deletion messages only show who deleted it, not the name of the deleted note or folder. | High
| If the chat is deleted by any user, there should be a notification of the deleted chat instead of the original one(referenced by whatsapp). | High | Done on Beta | Umar - Fixed on Beta
High
Multi-Domain Environment | We will implement a Multi-Domain Environment that enables the creation of separate domains for each company, such as AcePeak, MCM, and others. Each domain will function independently with its own dedicated email configuration, omnichannel setup, merchant gateway integration, CRM system, and AI tool API keys. Additionally, every domain will have the ability to customise its logo, profile settings, and minor UI colour elements to maintain brand identity. This structure ensures complete operational separation, secure configuration management, and independent control for each business entity within the platform. | High
Omnichannel Chat Integration: | MS Teams and Viber | High
| WhatsApp contacts, user/admin shall be able to send messages via contacts section/search contacts on WhatsApp omnichannel | High | Done | Anusha-Fixed
Phone: | The Recordings storage will be truncated after 7 days(if the add on plan is not bought). | High
| The Call Records Call history UI should have a back button to redirect on dialer. Reference UI design: CallHistoryUIBack-Improvement.png | High | Done | Anusha-Fixed
| There should be an auto call transcript option to the agent, manager or admin. | High | Done | Umar - Fixed on Beta
| Call Recordings deletion function for admin(and those users which admin is given access to). | High
| After Call feedback IVR Function shall be there to test. | High
Reports: | Campaign Log Reports - Historical record of all Campaign Calls for tracking. | High
| DID Log Reports - Historical record of types of DID numbers for basic tracking for Admin/Super-Admin. | High
High
Analytics: | Adoption Analytics - Track how features are being used by the team to ensure ROI. | High
| Business Analytics Pro: Advanced, customizable reports and deeper insights into trends. | High
High
High
Home: | Chat summary on Home dashboard | High
| The MCM brand logo should be replaced with the new one. | High
| A search Bar should be on top of the UI, where the user can search required functions (as per the figma design) | High
Auto Dialer (Agentless): | Eliminates agent interference and enables dialing via AI agents to maximize outbound productivity just like vapi. | High
Video: | Add a "Join" button in the notification section to directly join a meeting when invited. | High
| Add a ‘End Meeting’ button on this page to allow closing the meeting without opening it. End meeting button on ongoing meeting.png | High
DID Numbers: | 1. when the DID is released, that DID shall be released on next billing(so the user can revert the release before the billing). | High
| 2. DID purchase design structure should be better. | High
Department: | 1) Department extension number should be clearly visible alongside each department entry. | High
| 2) Department member count indicator should use a neutral/primary color (e.g., blue) instead of red. | High
| 3) The department manager name should appear directly below the department name to reflect hierarchy. as "Manager – <Name>" | High | Done
| Attachment: UI updates and improvement.png | High
| 4) add in the Users search bar Placeholder: “ Search by name or extension number ” | High | Done | Umar - Fixed
| Also in the Department tab search bar Placeholder: “ Search by name and extension number “ | High | Done | Umar - Fixed
High
CRM Integration- | Salesforce HubSpot Zoho CRM Microsoft Dynamics 365 Zendesk (Zendesk Sell) Pipedrive Freshsales (by Freshworks) Monday Sales CRM Copper CRM SugarCRM Insightly Oracle NetSuite | High
Plan: | Need to create plans for Europian countries. | High
| Need to create plans for rest of other countries. | High
Inbox: | Add search functionality in Message Inbox to find contacts by name or number | High | Done | Umar - Fixed on Beta
| MMS And Fax | High
CNAM (Caller Name Display): | Displays your company name on outbound calls to increase answer rates. | High
911 and other numbers Emergency Calling: | Mandates ability to connect to emergency services (Compliance), which needs an actual company address. Reference: https://en.wikipedia.org/wiki/List_of_emergency_telephone_numbers#:~:text=In%20many%20countries%2C%20dialing%20either,180 | High
Visual Call Flow/Work Flow Designer: | Drag-and-drop interface to easily configure how calls are routed (IVR). | High
Cost Center Management: | Track usage and allocate costs to specific departments. | High
Call Duration Limits: | Force disconnect calls after X minutes (useful for sales/support limits). | High
addon purchase Billing
Core Telephony & Call Handling
0 | Description
SIP Trunking – Auto Device Provisioning | Automatically configures SIP phones (Cisco, Yealink, Polycom, etc.) without manual credential setup, simplifying deployment.
SIP Trunking – Multi-Vendor Auto Provisioning | Enables zero-touch provisioning for multiple SIP-compatible devices across locations.
Call Routing Logic (Advanced Engine) | Intelligent rule-based routing based on caller ID, time, IVR input, agent availability, and queue status.
Dynamic Routing | Real-time routing adjustments based on queue length, agent load, or live performance metrics.
Skill-Based Routing (Basic Model) | Routes calls to agents based on defined skill tags.
Advanced ACD Framework | Full Automatic Call Distribution system managing high-volume inbound calls with intelligent logic.
Priority-Based Routing | Allows VIP or urgent callers to be prioritised in queues.
Data-Driven Routing (CRM Based) | Routes calls using CRM/customer history data.
IVR + ACD Integration | IVR collects caller input and feeds routing engine for intelligent distribution.
Estimated Wait Time | Announces live wait time and queue position.
Callback in Queue | Offers caller a callback option instead of waiting on hold.
Real-Time Queue Monitoring | Live supervisor view of queue metrics and agent states.
ACD Reporting & Analytics | Historical queue performance, SLA tracking, abandonment rate analysis.
Specific Routing & Omnichannel
Feature | Description
Omnichannel ACD | Unified routing across voice, chat, email, and social channels.
AI-Based Routing | AI-Based Routing is a smart call routing method that uses artificial intelligence to decide which agent should handle a customer interaction. Instead of simply sending calls based on fixed rules like “longest idle” or “round robin,” the system looks at historical data such as past customer interactions, agent performance, resolution rates, customer satisfaction scores, and even sentiment. It then predicts which available agent is most likely to achieve the best outcome for that specific customer and routes the call accordingly.
Skills-Based Interaction Routing | Multi-channel routing based on agent skill mapping.
Attribute-Based Routing | Advanced routing using attributes like region, certification, or language.
Channel-Based Flows | Separate routing workflows per communication channel.
Visual Flow Designer | Drag-and-drop UI to design routing and IVR workflows.
Concurrency Limits | Controls number of simultaneous chats/emails per agent.
ACW Cancellation | Allows wrap-up state override for urgent interactions.
Omnichannel Auto/Manual Assignment | System assigns automatically or supervisor manually assigns interactions.
Digital Channel Integrations (Telegram, Viber, Lime, Twitter, LinkedIn, MS Teams) | Integration with major messaging and social platforms for unified routing.
Messaging & Collaboration
Feature | Description
Task Creation in Chat | Allows agents to assign and track tasks within chat conversations.
Unified Inbox | Single interface for SMS, voicemail, fax, and digital messages.
Video Conferencing
Feature | Description
Video Conferencing Integration | Native or integrated video meetings for customer or internal collaboration.
Large Meeting (1500 Participants) | Webinar-scale meeting capability with high participant capacity.
Whiteboarding | Shared collaborative drawing canvas in meetings.
Annotation | Draw/highlight on shared screen during meeting.
Save Whiteboards/Notes | Persistent storage of meeting collaboration content.
Live Translation | Real-time caption translation in multiple languages.
AI & Automation
Feature | Description
FlowBuilder | Visual builder for IVR and routing workflows.
FlowBuilder Templates | Industry-specific workflow templates.
AI Agent / IVA (Voice & Chat) | Conversational AI for automated customer support and call deflection.
Chat Real-Time Translation | Live AI translation of chat messages.
Auto Dialer Script Approval | Admin approval workflow for outbound scripts.
Auto-Scoring (Calls) | AI evaluates calls using predefined QA criteria.
Supervisor Assist (AI Alerts) | AI alerts supervisors about negative sentiment or compliance risk.
Generative AI Message Writer | AI drafts email/chat responses.
Grammar & Tone Assistant | AI suggests corrections and empathetic tone improvements.
AI in Analytics | Predictive workload forecasting and anomaly detection.
Real-Time Agent Assist | AI provides live suggestions during interactions.
AI Knowledge Base Search | AI surfaces relevant help articles automatically.
Real-Time Coaching (AI) | AI nudges agents during calls (empathy prompts, compliance reminders).
AI-Powered CSAT & Conversation Intelligence
Feature | Description
AI-Powered CSAT | Predictive CSAT scoring using sentiment, keyword, and behavioral analysis.
Emotion Detection | Identifies anger, frustration, joy, confusion.
Context Sensitivity (NLP) | Detects sarcasm, tone changes, contextual meaning.
Sentiment Scoring | Assigns numeric sentiment value to interactions.
Conversation Intelligence | Analyzes themes, resolution success, and agent performance impact.
Predictive CSAT Model | Generates CSAT for 100% interactions without surveys.
AI Scorecards | Automated QA scoring against predefined compliance & performance metrics.
Supervisor & Agent Experience
Feature | Description
Call Monitoring Groups | Configurable supervisor-to-agent monitoring permissions.
Screen Monitoring | Supervisors view agent desktop in real-time.
Real-Time Supervisor Dashboard | Live queue and agent performance view.
Call Reshuffle | Supervisors manually reassign queued calls.
Silent Monitoring with Analytics | AI-triggered alerts for long wait or negative sentiment calls.
Agent Scorecards | Performance dashboard for individual agents.
Leaderboards | Gamified ranking system based on KPIs.
Last Call History Context | Displays prior interaction context automatically.
System Administration & Management
Feature | Description
SCIM API Integration | Automated HR-based user provisioning and de-provisioning.
Bulk Provisioning Tools | CSV or mass import user creation.
SSO | Corporate login integration (SAML/OAuth).
Multi-Site Management | Partitioned management across business units/sites.
Divisions | Organizational segmentation for large enterprises.
Partitioned Phone Books | Restricted internal directory visibility by division.
Reporting & Analytics
Feature | Description
Real-Time Dashboards | Live queue, SLA, and agent performance metrics.
Wallboards | Large-screen configurable KPI display.
Real-Time Data API | External access to live system metrics.
Historical Reporting | Past performance trend analysis.
Standard Reports | Prebuilt KPI reports (AHT, SLA, Abandon Rate).
Custom Reports | User-defined reporting with filters and metrics.
BI Integration | Embedded or export to business intelligence tools.
Custom Analytics Export | Raw data export and API integration.
Security & Reliability
Feature | Description
High Availability (99.999%) | Redundant infrastructure ensuring minimal downtime.
Geo-Distributed Data Centers | Multi-region deployment for resilience.
Load Balancing & Failover | Automatic traffic rerouting during failure.
Disaster Recovery Plan | Backup and recovery framework with DR drills.
Encryption (TLS, SRTP, HTTPS) | Encrypts signalling and media in transit.
Encryption at Rest (AES-256) | Secures stored recordings and data.
MFA | Multi-factor authentication for enhanced login security.
Fraud Monitoring | Detects abnormal call patterns and toll fraud.
IP Access Control | Restricts platform access by IP range.
Audit Logs | Tracks admin actions and system changes.
GDPR/Compliance Controls | Data privacy compliance and deletion tools.
DLP & Data Masking | Detects and masks sensitive data in transcripts.
Call Quality Monitoring | QoS metrics and call health tracking.
Public Status Dashboard | Public uptime and system health page.

## IssuesBugs
path | message | work | team work
web
Profile-> incoming calls -> Forward Calls | Play Announcement is not working in User Profile of Phone tab. | pass | Anusha - Fixed
Call Dialer | Need to implement Phone Number Format with Country Code: +1 (555) 123-4567 | pass | Fixed now
call transfer to extension | When a call is made from the UCaaS web to a non-UCaaS number and then transferred to another UCaaS extension, the call connects successfully. Charges are deducted for the first user’s call log and charges are correct, but charges for the second user (extension transferred call recipient) are not shown in the call-log report. | Pending | Umar - Pending
transfer call report on external number | When the user transfers the call to an external number, the call duration and cost is not being considered on the master caller's call report. | Pending | Anusha - Pending
Call Merge | The MasterCaller stucks at call when all other recipiants are left. | couldnt reproduced | Okay, considered as FIxed, still We need to discuss this with furqan sir.
Dialer search bar | The user should be able to search saved contacts on the dialer, including users with their extension and contact number(which is added in user details). | Improvement | Saurabh - Pending
Recordings Charge | Need to implement call recordings charge on companies user base capping, and storage should be allotted differently | In Progress | Saurabh - Pending
Sentiment Analysis | The Sentiment analysis is not working as expected. | Need to Discuss | Saurabh - Pending
Voicemail Timeout issue | The voicemail stays longer than 30 seconds. | As discussed with tauseef Sir there is no logic to end the voicemail after 30 sec even the caller is leaving the message.. but it happens when no one speaks for 3 to 4 sec it will be disconected | Bhushra - Pending
Decline with message | On Inbound calls, Decline with message is not working, SMS cost prompt and DLC required(if needed) restriction shall be shown to the user. | pass | Saurabh - Pending
Free Call Minutes | Call charges are being deducted even after the free call minutes are finished. | Testing | Saurabh - Pending
Call Recording Deletion | if the recording storage is free, we'll delete all recordings after 7 days after notifying the user before certain time. | Confirmation pending from furkan sir | Improvement, confirmation pending from furqan sir
transfer calls | when the user does an extension call and then the same caller transfers the extension call to another extension, all calls will be disconnected immediately. |  | shailendra - pending
monitoring | In the Monitoring section, most features are not functioning correctly. Only Listen and Barge are available, and within Barge, functions like Mute, Transcripts, Hold, and others don’t work. The Campaign section shows no reports, and even when a campaign is opened, it still displays Monitoring – Call Queue at the top. Overall, the sections are not working properly. |  | shailendra - pending
Transcription | System does not keep transcription on when user close the Call UI and get back to transcription. | pass | Fixed now
Transcription in Hindi | Transcription in Hindi is not working now | Saurabh Please provide Azure details | We have already added card details, please use the same azure account as given with mcmcaptek9278@outlook.com
Call Monitoring | Except All Calls, All other call monitoring tabs are not working, also call queue waiting callers records are being stuck on tab |  | Saurabh - Pending
call recoring on in-coming call | On incoming calls, call recording starts automatically even when the call recording setting is disabled.
Chat>message | When typing a long message in the chat input field, pressing Shift + Ctrl to move to a new line instead moves the cursor directly to the bottom line. | In Progress | shailendra -pending
Team Chat> Deleted user | If a user is deleted, their name and profile avatar are not shown in their previous chat messages in the team group. |  | Umar/Pending
Chat AI Assistant | A chat AI assistant shall be included for user's quick & easy issue resolution as per the FIgma design given in "Screenshots/videorec URLs" column | Please provide video or Screenshot | We will discuss this in meeting with adnan sir
Chat Section | A member cannot ping/tag other members on team chat (for example, @admin) | In Progress | shailendra - pending
chat | the change group photo not available after creating a group. | In Progress | shailendra - pending
chat->emoji | There are some categories of emojis are missing, e.g., flags, | In Progress | shailendra - pending
Chat list | chat pic profile | NEED TO DISCUSS
Chat > adding notes | Formatting option labels are visible for a few milliseconds before the notes editor loads properly. |  | shailendra - fixed
Chat Delete access | If the user does not have access to delete, the user still can delete chats via team, favorites and direct tab | pass | shailendra - Fixed
Chat Reload Issue | sometimes the user cannot see previous messages and even previous does not reload automatically until the user refreshes the page | pass | shailendra - Fixed
Chat Reload and Jump to Bottom | To stabilize the feed, implement a top-loading spinner combined with CSS overflow-anchor: auto to prevent the view from jumping when older messages prepend. Additionally, add a floating "down-arrow" button that appears when the user scrolls up, providing a one-click shortcut to return to the latest message. | pass | Saurabh - Fixed
Click on Created folder | If the user clicks on created chat folder name via vague notification, then gets back on chat, the user will be redirected to the top of the chat. | pass | Anusha-Fixed
Chat> Click on Replied Message | Sometimes, when clicking on a reply message, it does not redirect to original message and instead shows the notification: ‘Original message not found. It might be in an older conversation.’ | pass | Anusha-Fixed
chat->folder | There is no character limit on note and folder names. | pass | Anusha-Fixed
Join Call Button | Join button which was removed, is still pending to connect ongoing team chat call. | pass | Umar/Fixed
Chat | While editing a message draft in one chat, switching to a different chat carries the same edited draft into the other chat. When the draft is sent, it is delivered to the original chat instead of the currently active chat. | pass | Umar/Fixed
Chat > NOTES | Deleted note activity redirects to notes instead of showing deleted state. Also group or team does not shows as it is whether the team name is in UPPERCASE or lowecase style | pass | shailendra - fixed
Team Chat> removed/left user | In a team group, if any user is removed or leaves the group, their name and profile avatar are not shown in their previous chat messages. | pass | Umar/Fixed
Reply chat | When replying to a message in one user’s chat and then opening another user’s chat, the typed reply message appears in the other user’s chat. | pass | Umar/Fixed
In Team Delete message | In Team group if any user delete chat message name of the user is not showing, who is deleted the message is not showing.
video - recording | When I click the recording icon during a meeting, it loads and starts recording, but the recording info—like how long it has been recording—doesn’t show. | pass | Pending/Bushra
Video Improvement Part | Suppose I scheduled a meeting for one hour later and switch to another tab to work. When the meeting time arrives, I should receive a system notification. However, no system notification is received. | pass | Pending/Bushra
join buttton in notification secction | Add a "Join" button in the notification section to directly join a meeting when invited. | pass | Pending/Bushra
join meeting multiple time | A user can join the same meeting multiple times from different tabs using the same ID and name, which is not expected behavior and should be fixed. 1. There is no user validation on checking if the user is already on a video call. | FIXED/ Lets Discuss this on call. | Bushra /pending
Join Meeting Via Link | If an unknown user joins the meeting via the URL link and enters only spaces in the Name field, the user is still able to join the meeting. | pass | Umar/Fixed
Campaign Dashboard | In the campaign dashboard, the agent report displays the wrong count of campaigns assigned to agents. | Please add video Couldn't reproduced | Bushra/pending
Settings - Video | When we set profile photo from android, on the web version, the user won't be able to remove that profile photo | pass | Umar - Fixed
Call Queues Creation | The custom made user role can't be the manager of a Call Queues, despite giving all permissions to that user role | discussed with raman | Anusha/Pending
admin - sms/calling rates | In Admin Settings → SMS/Calling Rates, only Outbound Rates are shown, without clearly indicating whether they are for SMS or calling. After selecting a country, landline and mobile rates appear, but SMS or calling is still not specified. Also, searching for Canada shows two landline rates. | pass | Umar - Not Fixed
IVR Function | The overall IVR UI is not user friendly and does not seem professional and has some Logical bugs, the media function development is not completely implemented, where the user should have features to make the text to speech audio in multiple voices and accents, sample designs are given in "Screenshots/videorec URLs" column | Improvement
IVR Function | The Generic Key press function does not work on IVR calls, such as if the IVR is set on pressing * to go back on previous menu and # to repeat the present menu, also there is not option for 0 digit keypress | tauseef Sir
User ID | multiple systems with a single user ID can call different users without knowing each other. | Discuss tauseef Sir
Dialed Numbers | After running the campaigns the connected calls number is not visible | (Working fine with not anwered), Unable to check answered (webhook issue) TESTING | Anusha/Not Fixed
Campaign >Campain Logs | In campaign call reports, the Notes option appears for certain calls even when the call status is Cancelled. | FIXED/ Please check this | Anusha/Pending
Create Campaign | While creating a campaign in media before submitting the campaign settings when the user changes the dialer the script is removed from it and during the campaign calls the script is empty. | Not an issue : We kept type in Script based on the dialer : When dialer is changed the Script will also should be selected as per dialer chosen. | Video Added
Campaign>Recording | When an agent does not have recording access at the agent level, call recording does not work during a campaign, even if recording is enabled in the campaign settings. | Discussed with Adnan.. | Video Added
Campaigns Reports | In some campaigns the notes are visible even when the call is getted cut | pass | Umar/Fixed
Preview Campaign | In the preview campaign, the number of connected calls is incorrect. Also, when we click on the connected calls, no information is displayed
Predictive Campaign | In the predictive campaign, transcripts are not working.
SMS-Search bar | The search bar is not working. | In Progress | Anusha/Partially Fixed
SMS-Search bar | names wth numbers saved in contacts and numbers used on which SMS are sent shall be visible on the search bar including users with their contact number(which is added in user details).. | Discuss | Anusha/Not Fixed
SMS -> Message | When the sms is sent from report a popup occurs no sufficient balance to send message but by clicking in confirm the message is sent | pass | Anusha/Fixed
Inbox > SMS Tab | Add search functionality in Message Inbox to find contacts by name or number |  | Umar/partially fixed search bar is added but not working.
SMS -> Message | Delivery Status Missing: The system does not notify if the SMS is sent, delivered, or failed.UCAAS | pass | But that's a mandatory function which other SMS apps provides.
SMS -> Message | In the Inbox, when I try to send a message to any number, a “"available_balance" is not allowed” pop-up appears, and the SMS is not sent. | Add video | Anusha/Fixed
Sms > Plans > Free SMS | Free SMS are not being deducted from given free SMS in plan -> Billing. |  | Anusha/Fixed
Inbox > SMS | Contact profile picture is not displayed in Inbox conversation list or contacts | FIXED/ Please check again working fine | Umar - Fixed
Contacts and Search bar | Users shall be added with their contact numbers and other info (which is added in user details).
update same contact issue | If a new contact is created for the first time in any company and the same contact is later created in another company, when the contact is updated, the username of the user who created it in the first company is shown on the updated contact.
| Added inventory numbers shall have their available features(sms/calls in/out) | pass | Umar/Fixed
While purchasing the DID, user shall see those features before billing parts.
Billing -> Plan | Billing → Plan → DID(s) tab, the cost of purchased DIDs is not displayed. | pass | New purchased DIDs cost showing already purchased DIDs cost not showing
Add User -> assign number | if creating bulk users(e.g more then 2 or 3 ) and assigning their DID numbers using the ‘Assign Now’ option after payment, the same DID is being added two-three times.
Add/Assign Same DID Number issue | Users from different companies are able to purchase and assign the same DID numbers at the same.
Deleted user visibility | Deleted users must not be visible in any actions, such as i) While starting a new chat or creating/editing team chat, deleted users still exists in group chat members list. ii) Users/Inventory/departments lists iii) Licence management list iv) DID inventory list(assigned DID will be un-assigned) v) IVR/Call Queues/any Forward to extension actions. vi) Any search bars, if it includes a separate users list. | pass | Anusha/Not Fixed
Password Reset Link Has No Expiration Time v1.2.8 | There is no time limit or expiration for the password reset link, as it remains valid regardless of when it is opened, though once used password reset link, will be expired when the user uses on second time, but it should notify as expired at initial screen after trying to use it second time. | FIXED/ Please explain which Scenario u are reffering to is not fixed or add video | Not Fixed
User owned DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin | Improvement | Anusha/Not Fixed
Overall UI responsiveness | When the user/admin does any change for another user, such as changing their role, creating a department or team chat and adding a scheduling and inviting other users/members, etc. The bug is that the application is not implementing real-time data updates and relies on manual page refreshes, which is an issue with frontend or backend communication, possibly a missing or improperly configured WebSocket connection, incorrect event handling, or issues with a live-reloading development server. The UI needs a mechanism like WebSockets or AJAX calls to listen for server-sent events and update the display dynamically, rather than waiting for the user to manually refresh | pass | Anusha/Not Fixed
Error 404 | Sometimes the Error 404 occurs on some accounts, on which upon clicking "Go To Homepage", The button does not redirect and refresh up on homepage | pass | Anusha/Fixed
Account Renewal | all users except admin, are able to login and use all functions(excluding billing related). |  | Anusha/Fixed
Knowledge base DB Collision | some companies are having the same knowledge bases created on a single company, this means all knowledge base records are being unified in several companies: | pass | Umar/Fixed
Login OTP | There should be an OTP attempt limit, for example: if the user is not able to insert otp correctly for 5 times | pass | Umar/Fixed
Login OTP | There is no otp expiration rule, such as after 10-15 mins the otp shall expire. | pass | Umar/Fixed
Home>Dashboard | In the Home Dashboard, the Outgoing graph is incorrectly including incoming ,voicemail, missed calls counts. | In Progress | Anusha/Pending
voicemail setting | Voicemail is not working. Even after enabling voicemail and setting an email address, the calls are not being forwarded to voicemail. Also the connect to voicemail does not work or unclarified. | Pending | Anusha/Pending
Profile | First, there is no option in the application to delete the profile picture, and there are synchronization issues between the web and the application. While the profile picture syncs correctly when uploaded, deleting it requires logging out and then logging back into the application for the change to take effect. Also the user cannot remove that profile photo from web app. and upon Logging into others account, the same profile photo will be set on android app. | pass | Anusha/Not Fixed .After the removing the profile too its not getting removed
Home -> Admin controls | Call forwarding is not functioning. If we set any value (such as forwarding to an external number) and click Save Changes, the values are not saved. Also on UI, the user is able to forward calls on its own extension. | pass | Umar/Fixed
Home | There is currently no option in the UCaaS application to view the account balance. | pass | Umar/Fixed
Phone calls | During a DID call, when clicking on the Transfer option, there is no option available to transfer or speak the call to an external number. | Testing
Dialer | if call Recipient declines the extension call but it keeps ringing on the caller side until the ring timeout ends, and then it stops. | It happens due to multiple logins
Home > User | During extension calls, the call disconnects for both parties when transferring the call.
Transfer Call | When a user makes an extension call and then transfers that call to another extension, all calls get disconnected immediately. | Testing
Home>Extension Calls | During extension calls, when the user clicks on the transfer option, a number search bar appears. Currently, typing any number in this bar can transfer the call to an external number. However, the transfer feature should only allow searching for and selecting extension numbers or user names within the system, | pass | Umar/Fixed
Phone calls > Filter | In the phone call section, the filter options are not working as follows: This Week Last 7 Days This Month Last 30 Days Last Month | Already working Fine | Working
Dialer | There should be a proper flow for outbound calls, including connecting, calling, and ringing. | pass | Umar/Fixed
Dialer | The caller’s phone is ringing, but the agent’s phone still shows “calling". | pass | Umar/Fixed
inbox | The search functionality does not Exist. | pass | Umar/Fixed
Invite Members | In Invite Members, once members are selected and you navigate away and return, the selected members are not shown as checked, even though they are still selected. | Done | Umar - Fixed
Video Meeting | When an Android user joins a meeting as a guest, and host is a web user if the host tries to turn off the Android user’s camera access, it does not work.
Video Meeting | In the video call section the features are missing: 1. Recording 2. Screen Sharing 3. Reaction options 4. Chat feature 5. Info option (with share invite link) 6. Participants and host accesses 7. Background effects 8. Presentation mode 9. invite other users via email | 1.Chat Feature Done 2.Reaction option Done 3.Info(Invite) option Done 4.Participants Done 5.Recording Feature Done 6.Screen share 7.invite other users via email(Add)Done | Given points are added. but screen share is not working.
Video Meeting | There is a screen size/layout issue in meetings. When a user joins with a web participant, the web user’s video does not display properly. same as for screen share UI. | Done | Image added
Past Meetings | In past meetings, clicking on attendees does not show the user information. | pass | Umar/Fixed
Feedback | The feedback option does not exist | pass | Umar/Fixed
Video Meeting | When starting a recording, a popup appears saying "Failed to start," but the recording actually begins after clicking OK. Similarly, when stopping the recording, a popup shows "Participant left." | pass | Umar/Fixed
Video Meeting | If a meeting is scheduled with a password, all meeting details are shown later, but the set password is not displayed. | pass | Umar/Fixed
Emoji | In the Chat section, only a limited number of emojis are visible. | pass | add but not in separate sections format
Chats | When I delete a folder and notes that I created in the chat section, it does not show the name of the folder and notes that is being deleted. | Same as web
Chats | When an Android user deletes a team chat, it is removed from both the Android app and the web app. However, the user is not removed from the group—only the team chat is deleted. The user still appears in the group, and if any user calls this deleted group, the call still rings. | Please check again | Fixed .But the member left the group notification didnt camed .
Chats | In the chat section, when one user sends a file, the chat messages keep loading, and the document takes time to open | pass | Anusha/Fixed
Chats | When replying with a document (such as an image or any other file), the document is not shown in the replied chat. | Done | Umar/Not Fixed
Chats | In Chats, when selecting any chat, the selected chat is not highlighted properly. | pass | Anusha/Not Fixed
chats ->Sended File | Change thisDownload File icon.jpeg on the chat to the given icon shown in the sample icon image. | pass | Anusha/Not Fixed
Team chat | The team chat is not working in real time. When an Android user sends a message in a group, the message does not appear on the web. It only shows after refreshing the page. 1 to 1 chat working fine. | In progress
Chat Call | If a user makes a chat call to an Android user and the Android user ends the call, the Android user leaves the call but the web user remains in the call. Similarly, if the web user ends the call, the Android user remains in the call. the call not ended for both side. | Testing
Chats | Whenever a user sends a message to another user, a notification should appear on the screen. | pass | Notification working, but upon clicking on chat message. user does not redirect to the specific chat, and mark as read is also not working.
Start Call | In the Start Call feature, the mute option is not visible, so the user cannot see whether they are muted or unmuted. | pass | Umar/Fixed
Call Duration | The call duration is shown as 0:00, and the actual duration is not being recorded. | pass | Umar/Fixed
Folder>Files | When clicking multiple times to add files, the same file gets added to the folder multiple times. | pass | Umar/Fixed
Edit Message | In the Chat section, even older messages can be edited. | pass | Umar/Fixed
Start Call | Even when a user is offline, the “Start Call” option is shown. It should instead display “User Unavailable.” | pass | Umar/Fixed
Direct Message | When clicking on Direct Message and searching by member, the member names do not appear in the dropdown. | pass | Umar/Fixed
Chats | In the chat section, users cannot delete messages by; they selecting all can only delete messages one at a time | Done (Multi Selection Implmented) | Umar/Fixed
Chats | In the chat section the features are missing on the user chat side: • Remove option • Read and Mark option | pass | Umar/Fixed
Chats | Same as web app, if other member/other user deletes a message, still the user will be able to see on the chat preview | pass | Umar/Fixed
Initial Permissions Access Request | The app should directly ask for permissions like camera access, sms access, etc. on start of the application and there should be an optional prompt to ignore some unnecessary permissions as "do not ask again", unless the user tries to access those functions on which the system needs those accesses (such as camera, nearby devices, location, media, etc).
Contact | In the Contact section, the “Created By” and “Updated By” information is not visible. | Testing | Anusha/Fixed
Contact>Activity Logs | In the Contact section, the activity logs are not showing any information. | Done | Umar/Not Fixed
Contact>SMS | When sending an SMS through the Contact section, the country code is predefined as +1. If the number already includes the country code, it gets added again, resulting in two country codes. | Testing | Anusha/Fixed
Contact>Edit Contact | When editing a contact, the gender field is not being updated. | Done | Umar/Fixed
Contact >Birth Date | In the contact section, the birth date field only allows selecting today’s date. | pass | Umar/Fixed
Contact | In the Contact section, the sms icon is displayed instead of the chat icon. | pass | Umar/Fixed
Company -> Users | create the user and select the other roles but, the created user’s role is displayed as Admin in the UCaaS application. | pass | Umar/ Fixed
Company -> Users | New created user is not assigned to the already purchased license, and the created user is not shown in the Billing Licenses section. | In Progress
Company -> Users | When added a user from Super Admin and logs in this created user, only the Home, Phone, and Admin sections are visible after login. | In Progress | Umar/ Fixed
Rate Card -> Rate Card Details | Pagination page-size selector UI issue: When clicking on the page-size dropdown, the dropdown values appear behind the table and are not visible. | pass | Dropdown is showing but Its not working. Filter Pagination issue.mp4
UCaaS Super-Admin - DID numbers https://admin-ucaas.mycountrymobile.com/ | If the Super-Admn deletes a user's DID number, it does not get deleted from the user account, and still the user is able to use that DID number. | pass | The number is deleted, but if it is assigned to a user, it is not removed from the user, and the user can continue using it until the number is changed.
The Company->admin Login | The Super admin is not able login with the given company's admin login option | pass | Umar/Fixed
Company dashboard | Company dashboard | pass | Umar/Not Fixed and also the graph name has been changed. It was “Yearly Meeting summary” but it has been changed to “Yearly Company summary.”
User's own DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin | DONE and need to discuss
Home Dashboard | Need to rename the 'new company' as 'active company', which is not appearing on the superadmin home dashboard. | pass | Umar/ Fixed on beta
Companies-> Profile | When the company name is updated, the changes are not reflected in the customer portal, but still it is updated correctly in the Super Admin panel, also the company name is editable with the same name as per the other company. | ADD VIDEO | Video Added
Companies->Dashboard | The company dashboard graphs are inaccurate and displaying incorrect information. | pass | Umar/ Fixed on beta
Companies-> Profile | In the Company Info section, the total number of members and the number of DIDs purchased are not shown properly which seems incorrect. | pass | Not Fixed properly, need to discuss this
Companies->Calls->Filter | In Companies > Calls > Filter > Select Type, “Missed Calls” and “Voicemail” are not visible and are incorrectly listed under “Inbound Calls.” | Done | Umar/Not Fixed
Video Meetings | In the Duration column, incorrect durations are shown for all meetings (01:00 for instant meetings and 00:15 for scheduled meetings) | Format fixed on qa | Not Fixed
Companies->Virtual Number ->Search Bar | search bar is not working in Virtual Number section. | FIXED - Added search on number , name and assingTo name | Umar/ Fixed on beta
SMS-> search | The ‘Select Date’ dropdown is not working and shows the error message ‘Something went wrong.’ | FIXED on Qa | Umar/ Fixed on beta
SMS-> search | Search bar is not working. | pass | Umar/ Fixed on beta
DID Number-> assigned DID | In the search bar, searching by number is not working and no results are shown. |  | Umar/ Fixed on beta
DID Number-> Unassigned DID | In Unassigned DID section the any Unassigned DID number not showing.
Companies->Virtual Number ->Filter | In the Companies -> Virtual Numbers section, the “Select DID Type” filter currently shows only two options: Local and Toll-Free. The Mobile type option is missing, and the search bar in the Select Type dropdown is not required and should be removed. | pass | Umar/Fixed
Scheduled Meeting and event | When any company user schedules or creates an event, the scheduled meeting or event appears in the Video Meeting section of all companies. | pass | Umar/Fixed
Companies->Video Meetings | In the Upcoming Meetings section, the “Select Type” and “Select Status” dropdowns include a search bar, which is not required and should be removed. | pass | Umar/Fixed
UCaaS Super-Admin https://admin-ucaas.mycountrymobile.com/ | In the Super-Admin UI, the admin is not able to make a user's account deactivate or expire, upon using on these functions, those user will be logged out only. and after logging in again, it will fetch some errors, but can still work with their account. | pass | Umar/Fixed
Video Meetings | In Video Meeting → Search Filter, when selecting the Scheduled type, no results are displayed even though meetings exist. | pass | Umar/Fixed
Companies->Video Meetings | In Video Meetings, the label “Attendees” should be changed to “Invitees.” | pass | Umar/Fixed
Companies->Video Meetings | In the Past Meetings section, when filtering by status “Complete,” an error popup appears saying “Something went wrong.” | pass | Umar/Fixed
Companies | When Search any company in the search result the company plan name is not showing. | pass | Umar/Fixed
Companies->Calls->Filter | In Companies > Calls > Filter > Select Date, when selecting “Last 7 Days,” records from 8 days are being displayed. | fixed on qa
Companies->Calls->Filter | In Companies > Calls > Filter, the “Enter Name” search is not working. | pass | Umar/Fixed

## IssuesBugs of Beta version
path | message | work | team work
web
call transfer to extension | When a call is made from the UCaaS web to a non-UCaaS number and then transferred to another UCaaS extension, the call connects successfully. Charges are deducted for the first user’s call log and charges are correct, but charges for the second user (extension transferred call recipient) are not shown in the call-log report. | Pending | Umar - Pending
transfer call report on external number | When the user transfers the call to an external number, the call duration and cost is not being considered on the master caller's call report. | Pending | Anusha - Pending
Call Merge | The MasterCaller stucks at call when all other recipiants are left. | couldnt reproduced | Okay, considered as FIxed, still We need to discuss this with furqan sir.
Dialer search bar | The user should be able to search saved contacts on the dialer, including users with their extension and contact number(which is added in user details). | Improvement | Saurabh - Pending
Recordings Charge | Need to implement call recordings charge on companies user base capping, and storage should be allotted differently | In Progress | Saurabh - Pending
Sentiment Analysis | The Sentiment analysis is not working as expected. | Need to Discuss | Saurabh - Pending
Voicemail Timeout issue | The voicemail stays longer than 30 seconds. | As discussed with tauseef Sir there is no logic to end the voicemail after 30 sec even the caller is leaving the message.. but it happens when no one speaks for 3 to 4 sec it will be disconected | Bhushra - Pending
Decline with message | On Inbound calls, Decline with message is not working, SMS cost prompt and DLC required(if needed) restriction shall be shown to the user. | pass | Saurabh - Pending
Free Call Minutes | Call charges are being deducted even after the free call minutes are finished. | Testing | Saurabh - Pending
Call Recording Deletion | if the recording storage is free, we'll delete all recordings after 7 days after notifying the user before certain time. | Confirmation pending from furkan sir | Improvement, confirmation pending from furqan sir
transfer calls | when the user does an extension call and then the same caller transfers the extension call to another extension, all calls will be disconnected immediately. | when the user does an extension call and then the same caller transfers the extension call to another extension, The call will be connected between other two and disconnected for who has initiated the transfer | shailendra - pending
monitoring | In the Monitoring section, most features are not functioning correctly. Only Listen and Barge are available, and within Barge, functions like Mute, Transcripts, Hold, and others don’t work. The Campaign section shows no reports, and even when a campaign is opened, it still displays Monitoring – Call Queue at the top. Overall, the sections are not working properly. | pass | shailendra - pending
Transcription | System does not keep transcription on when user close the Call UI and get back to transcription. | pass | Saurabh - pending(transcription is not working for now)
Transcription in Hindi | Transcription in Hindi is not working now | Saurabh Please provide Azure details | We have already added card details, please use the same azure account as given with mcmcaptek9278@outlook.com
Call Monitoring | Except All Calls, All other call monitoring tabs are not working, also call queue waiting callers records are being stuck on tab | pass | Saurabh - Pending
Call Dialer | Need to implement Phone Number Format with Country Code: +1 (555) 123-4567 | pass | Fixed now
Profile-> incoming calls -> Forward Calls | Play Announcement is not working in User Profile of Phone tab. | pass | Anusha - Fixed
call recoring on in-coming call | On incoming calls, call recording starts automatically even when the call recording setting is disabled.
Phone | The transcript or recording feature is not working on phone |  | Bushra -Pending
call merge | Call merge is not working. |  | shailendra - pending
incoming calls | Incoming calls are not working. |  | shailendra - pending
Call history | Call history does not display after calling |  | Bushra -Pending
Chat>message | When typing a long message in the chat input field, pressing Shift + Ctrl to move to a new line instead moves the cursor directly to the bottom line. | pass | shailendra -pending
Team Chat> Deleted user | If a user is deleted, their name and profile avatar are not shown in their previous chat messages in the team group. |  | Umar/Pending
Chat > adding notes | Formatting option labels are visible for a few milliseconds before the notes editor loads properly. | pass | shailendra - fixed
Chat AI Assistant | A chat AI assistant shall be included for user's quick & easy issue resolution as per the FIgma design given in "Screenshots/videorec URLs" column | Please provide video or Screenshot | We will discuss this in meeting with adnan sir
Chat Section | A member cannot ping/tag other members on team chat (for example, @admin) | pass | shailendra - pending
chat | the change group photo not available after creating a group. | pass | shailendra - pending
chat->emoji | There are some categories of emojis are missing, e.g., flags, | In Progress | shailendra - pending
Chat list | chat pic profile | NEED TO DISCUSS
Chat Delete access | If the user does not have access to delete, the user still can delete chats via team, favorites and direct tab | pass | shailendra - Fixed
Chat Reload Issue | sometimes the user cannot see previous messages and even previous does not reload automatically until the user refreshes the page | pass | shailendra - Fixed
Chat Reload and Jump to Bottom | To stabilize the feed, implement a top-loading spinner combined with CSS overflow-anchor: auto to prevent the view from jumping when older messages prepend. Additionally, add a floating "down-arrow" button that appears when the user scrolls up, providing a one-click shortcut to return to the latest message. | pass | Saurabh - Fixed
Click on Created folder | If the user clicks on created chat folder name via vague notification, then gets back on chat, the user will be redirected to the top of the chat. | pass | Anusha-Fixed
Chat> Click on Replied Message | Sometimes, when clicking on a reply message, it does not redirect to original message and instead shows the notification: ‘Original message not found. It might be in an older conversation.’ | pass | Anusha-Fixed
chat->folder | There is no character limit on note and folder names. | pass | Anusha-Fixed
Join Call Button | Join button which was removed, is still pending to connect ongoing team chat call. | pass | Umar/Fixed
Chat | While editing a message draft in one chat, switching to a different chat carries the same edited draft into the other chat. When the draft is sent, it is delivered to the original chat instead of the currently active chat. | pass | Umar/Fixed
Chat > NOTES | Deleted note activity redirects to notes instead of showing deleted state. Also group or team does not shows as it is whether the team name is in UPPERCASE or lowecase style | pass | shailendra - fixed
Team Chat> removed/left user | In a team group, if any user is removed or leaves the group, their name and profile avatar are not shown in their previous chat messages. | pass | Umar/Fixed
Reply chat | When replying to a message in one user’s chat and then opening another user’s chat, the typed reply message appears in the other user’s chat. | pass | Umar/Fixed
In Team Delete message | In Team group if any user delete chat message name of the user is not showing, who is deleted the message is not showing. | pass
Chat Section | Error appears when sharing image in chat | pass | Bushra - pending
pass
video - recording | When I click the recording icon during a meeting, it loads and starts recording, but the recording info—like how long it has been recording—doesn’t show. | pass | Pending/Bushra
Video Improvement Part | Suppose I scheduled a meeting for one hour later and switch to another tab to work. When the meeting time arrives, I should receive a system notification. However, no system notification is received. | pass | Pending/Bushra
join buttton in notification secction | Add a "Join" button in the notification section to directly join a meeting when invited. | pass | Pending/Bushra
join meeting multiple time | A user can join the same meeting multiple times from different tabs using the same ID and name, which is not expected behavior and should be fixed. 1. There is no user validation on checking if the user is already on a video call. | pass | Bushra /pending
Join Meeting Via Link | If an unknown user joins the meeting via the URL link and enters only spaces in the Name field, the user is still able to join the meeting. | pass | Umar/Fixed
Video Meeting | Unable to join meeting via UCCAS site, but can join through email link |  | Pending/Bushra
Campaign Dashboard | In the campaign dashboard, the agent report displays the wrong count of campaigns assigned to agents. | pass | Bushra/pending
Settings - Video | When we set profile photo from android, on the web version, the user won't be able to remove that profile photo | pass | Umar - Fixed
Call Queues Creation | The custom made user role can't be the manager of a Call Queues, despite giving all permissions to that user role | discussed with raman | Anusha/Pending
admin - sms/calling rates | In Admin Settings → SMS/Calling Rates, only Outbound Rates are shown, without clearly indicating whether they are for SMS or calling. After selecting a country, landline and mobile rates appear, but SMS or calling is still not specified. Also, searching for Canada shows two landline rates. | pass | Umar - Not Fixed
IVR Function | The overall IVR UI is not user friendly and does not seem professional and has some Logical bugs, the media function development is not completely implemented, where the user should have features to make the text to speech audio in multiple voices and accents, sample designs are given in "Screenshots/videorec URLs" column | Improvement
IVR Function | The Generic Key press function does not work on IVR calls, such as if the IVR is set on pressing * to go back on previous menu and # to repeat the present menu, also there is not option for 0 digit keypress | tauseef Sir
User ID | multiple systems with a single user ID can call different users without knowing each other. | Discuss tauseef Sir
Dialed Numbers | After running the campaigns the connected calls number is not visible | (Working fine with not anwered), Unable to check answered (webhook issue) TESTING | Anusha/Not Fixed
Campaign >Campain Logs | In campaign call reports, the Notes option appears for certain calls even when the call status is Cancelled. | FIXED/ Please check this | Bushra/Fixed
Create Campaign | While creating a campaign in media before submitting the campaign settings when the user changes the dialer the script is removed from it and during the campaign calls the script is empty. | Not an issue : We kept type in Script based on the dialer : When dialer is changed the Script will also should be selected as per dialer chosen. | Video Added
Campaign>Recording | When an agent does not have recording access at the agent level, call recording does not work during a campaign, even if recording is enabled in the campaign settings. | Discussed with Adnan.. | Video Added
Campaigns Reports | In some campaigns the notes are visible even when the call is getted cut | pass | Umar/Fixed
SMS-Search bar | The search bar is not working. | pass | shailendra - fixed
SMS-Search bar | names wth numbers saved in contacts and numbers used on which SMS are sent shall be visible on the search bar including users with their contact number(which is added in user details).. | Discuss | Anusha/Not Fixed
SMS -> Message | When I send an SMS from the inbox, I get a popup message saying 'SMS sending failed | pass | shailendra - pending
Inbox > SMS Tab | Add search functionality in Message Inbox to find contacts by name or number |  | shailendra - fixed
SMS -> Message | Delivery Status Missing: The system does not notify if the SMS is sent, delivered, or failed.UCAAS | pass | But that's a mandatory function which other SMS apps provides.
SMS -> Message | In the Inbox, when I try to send a message to any number, a “"available_balance" is not allowed” pop-up appears, and the SMS is not sent. | pass | Anusha/Fixed
Sms > Plans > Free SMS | Free SMS are not being deducted from given free SMS in plan -> Billing. |  | Anusha/Fixed
SMS | SMS messages are not being sent in the SMS section |  | Bushra pending
Inbox > SMS | Contact profile picture is not displayed in Inbox conversation list or contacts | FIXED/ Please check again working fine | shailendra - pending
Inbox | Inbox index section layout misaligned |  | Bushra pending
Contacts and Search bar | Users shall be added with their contact numbers and other info (which is added in user details).
update same contact issue | If a new contact is created for the first time in any company and the same contact is later created in another company, when the contact is updated, the username of the user who created it in the first company is shown on the updated contact.
contact | I don’t have a DID number, but when I try to call from contacts, the call goes through and then shows “trying to call on this number is not available.” |  | Bushra Pending
| Added inventory numbers shall have their available features(sms/calls in/out) | pass | Umar/Fixed
While purchasing the DID, user shall see those features before billing parts.
Billing -> Plan | Billing → Plan → DID(s) tab, the cost of purchased DIDs is not displayed. | pass | New purchased DIDs cost showing already purchased DIDs cost not showing
Add User -> assign number | if creating bulk users(e.g more then 2 or 3 ) and assigning their DID numbers using the ‘Assign Now’ option after payment, the same DID is being added two-three times.
Add/Assign Same DID Number issue | Users from different companies are able to purchase and assign the same DID numbers at the same.
Number | When I purchase a DID number, it shows ‘Something went wrong |  | Bushra Pending
Deleted user visibility | Deleted users must not be visible in any actions, such as i) While starting a new chat or creating/editing team chat. ii) Users/Inventory/departments lists iii) Licence management list iv) DID inventory list(assigned DID will be un-assigned) v) IVR/Call Queues/any Forward to extension actions. vi) Any search bars, if it includes a separate users list. | pass | Anusha/Not Fixed
ai | ai tools not working |  | shailendra - pending
Password Reset Link Has No Expiration Time v1.2.8 | There is no time limit or expiration for the password reset link, as it remains valid regardless of when it is opened, though once used password reset link, will be expired when the user uses on second time, but it should notify as expired at initial screen after trying to use it second time. | FIXED/ Please explain which Scenario u are reffering to is not fixed or add video | Not Fixed
User owned DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin | Improvement | Anusha/Not Fixed
Overall UI responsiveness | When the user/admin does any change for another user, such as changing their role, creating a department or team chat and adding a scheduling and inviting other users/members, etc. The bug is that the application is not implementing real-time data updates and relies on manual page refreshes, which is an issue with frontend or backend communication, possibly a missing or improperly configured WebSocket connection, incorrect event handling, or issues with a live-reloading development server. The UI needs a mechanism like WebSockets or AJAX calls to listen for server-sent events and update the display dynamically, rather than waiting for the user to manually refresh | pass | Anusha/Not Fixed
Error 404 | Sometimes the Error 404 occurs on some accounts, on which upon clicking "Go To Homepage", The button does not redirect and refresh up on homepage | pass | Anusha/Fixed
Account Renewal | all users except admin, are able to login and use all functions(excluding billing related). |  | Anusha/Fixed
Knowledge base DB Collision | some companies are having the same knowledge bases created on a single company, this means all knowledge base records are being unified in several companies: | pass | Umar/Fixed
Login OTP | There should be an OTP attempt limit, for example: if the user is not able to insert otp correctly for 5 times | pass | Umar/Fixed
Login OTP | There is no otp expiration rule, such as after 10-15 mins the otp shall expire. | pass | Umar/Fixed
Home>Dashboard | In the Home Dashboard, the Outgoing graph is incorrectly including incoming ,voicemail, missed calls counts. | In Progress | Anusha/Pending
voicemail setting | Voicemail is not working. Even after enabling voicemail and setting an email address, the calls are not being forwarded to voicemail. Also the connect to voicemail does not work or unclarified. | Pending | Anusha/Pending
Profile | First, there is no option in the application to delete the profile picture, and there are synchronization issues between the web and the application. While the profile picture syncs correctly when uploaded, deleting it requires logging out and then logging back into the application for the change to take effect. Also the user cannot remove that profile photo from web app. and upon Logging into others account, the same profile photo will be set on android app. | pass | Anusha/Not Fixed .After the removing the profile too its not getting removed
Home -> Admin controls | Call forwarding is not functioning. If we set any value (such as forwarding to an external number) and click Save Changes, the values are not saved. Also on UI, the user is able to forward calls on its own extension. | pass | Umar/Fixed
Home | There is currently no option in the UCaaS application to view the account balance. | pass | Umar/Fixed
Phone calls | During a DID call, when clicking on the Transfer option, there is no option available to transfer or speak the call to an external number. | Testing
Dialer | if call Recipient declines the extension call but it keeps ringing on the caller side until the ring timeout ends, and then it stops. | It happens due to multiple logins
Home > User | During extension calls, the call disconnects for both parties when transferring the call. | In Progress
Transfer Call | When a user makes an extension call and then transfers that call to another extension, all calls get disconnected immediately. | Testing
Home>Extension Calls | During extension calls, when the user clicks on the transfer option, a number search bar appears. Currently, typing any number in this bar can transfer the call to an external number. However, the transfer feature should only allow searching for and selecting extension numbers or user names within the system, | pass | Umar/Fixed
Phone calls > Filter | In the phone call section, the filter options are not working as follows: This Week Last 7 Days This Month Last 30 Days Last Month | Already working Fine | Working
Dialer | There should be a proper flow for outbound calls, including connecting, calling, and ringing. | pass | Umar/Fixed
Dialer | The caller’s phone is ringing, but the agent’s phone still shows “calling". | pass | Umar/Fixed
inbox | The search functionality does not Exist. | pass | Umar/Fixed
Invite Members | In Invite Members, once members are selected and you navigate away and return, the selected members are not shown as checked, even though they are still selected. | pass | Umar - Fixed
Video Meeting | When an Android user joins a meeting as a guest, and host is a web user if the host tries to turn off the Android user’s camera access, it does not work.
Video Meeting | In the video call section the features are missing: 1. Recording 2. Screen Sharing 3. Reaction options 4. Chat feature 5. Info option (with share invite link) 6. Participants and host accesses 7. Background effects 8. Presentation mode 9. invite other users via email | 1.Chat Feature Done 2.Reaction option Done 3.Info(Invite) option Done 4.Participants Done 5.Recording Feature Done 6.Screen share 7.invite other users via email(Add)Done | Given points are added. but screen share is not working.
Video Meeting | There is a screen size/layout issue in meetings. When a user joins with a web participant, the web user’s video does not display properly. same as for screen share UI. | Done | Image added
Past Meetings | In past meetings, clicking on attendees does not show the user information. | pass | Umar/Fixed
Feedback | The feedback option does not exist | pass | Umar/Fixed
Video Meeting | When starting a recording, a popup appears saying "Failed to start," but the recording actually begins after clicking OK. Similarly, when stopping the recording, a popup shows "Participant left." | pass | Umar/Fixed
Video Meeting | If a meeting is scheduled with a password, all meeting details are shown later, but the set password is not displayed. | pass | Umar/Fixed
Emoji | In the Chat section, only a limited number of emojis are visible. | pass | add but not in separate sections format
Chats | When I delete a folder and notes that I created in the chat section, it does not show the name of the folder and notes that is being deleted. | Same as web
Chats | When an Android user deletes a team chat, it is removed from both the Android app and the web app. However, the user is not removed from the group—only the team chat is deleted. The user still appears in the group, and if any user calls this deleted group, the call still rings. | Please check again | Fixed .But the member left the group notification didnt camed .
Chats | In the chat section, when one user sends a file, the chat messages keep loading, and the document takes time to open | pass | Anusha/Fixed
Chats | When replying with a document (such as an image or any other file), the document is not shown in the replied chat. | pass | Umar/Not Fixed
Chats | In Chats, when selecting any chat, the selected chat is not highlighted properly. | pass | Anusha/Not Fixed
chats ->Sended File | Change thisDownload File icon.jpeg on the chat to the given icon shown in the sample icon image. | pass | Anusha/Not Fixed
Team chat | The team chat is not working in real time. When an Android user sends a message in a group, the message does not appear on the web. It only shows after refreshing the page. 1 to 1 chat working fine. | In progress
Chat Call | If a user makes a chat call to an Android user and the Android user ends the call, the Android user leaves the call but the web user remains in the call. Similarly, if the web user ends the call, the Android user remains in the call. the call not ended for both side. | Testing
Chats | Whenever a user sends a message to another user, a notification should appear on the screen. | pass | Notification working, but upon clicking on chat message. user does not redirect to the specific chat, and mark as read is also not working.
Start Call | In the Start Call feature, the mute option is not visible, so the user cannot see whether they are muted or unmuted. | pass | Umar/Fixed
Call Duration | The call duration is shown as 0:00, and the actual duration is not being recorded. | pass | Umar/Fixed
Folder>Files | When clicking multiple times to add files, the same file gets added to the folder multiple times. | pass | Umar/Fixed
Edit Message | In the Chat section, even older messages can be edited. | pass | Umar/Fixed
Start Call | Even when a user is offline, the “Start Call” option is shown. It should instead display “User Unavailable.” | pass | Umar/Fixed
Direct Message | When clicking on Direct Message and searching by member, the member names do not appear in the dropdown. | pass | Umar/Fixed
Chats | In the chat section, users cannot delete messages by; they selecting all can only delete messages one at a time | pass | Umar/Fixed
Chats | In the chat section the features are missing on the user chat side: • Remove option • Read and Mark option | pass | Umar/Fixed
Chats | Same as web app, if other member/other user deletes a message, still the user will be able to see on the chat preview | pass | Umar/Fixed
Initial Permissions Access Request | The app should directly ask for permissions like camera access, sms access, etc. on start of the application and there should be an optional prompt to ignore some unnecessary permissions as "do not ask again", unless the user tries to access those functions on which the system needs those accesses (such as camera, nearby devices, location, media, etc).
Contact | In the Contact section, the “Created By” and “Updated By” information is not visible. | pass | Anusha/Fixed
Contact>Activity Logs | In the Contact section, the activity logs are not showing any information. | Done | Umar/Not Fixed
Contact>SMS | When sending an SMS through the Contact section, the country code is predefined as +1. If the number already includes the country code, it gets added again, resulting in two country codes. | pass | Anusha/Fixed
Contact>Edit Contact | When editing a contact, the gender field is not being updated. | pass | Umar/Fixed
Contact >Birth Date | In the contact section, the birth date field only allows selecting today’s date. | pass | Umar/Fixed
Contact | In the Contact section, the sms icon is displayed instead of the chat icon. | pass | Umar/Fixed
Company -> Users | create the user and select the other roles but, the created user’s role is displayed as Admin in the UCaaS application. | pass | not fixed properly, need to discuss this
Company -> Users | New created user is not assigned to the already purchased license, and the created user is not shown in the Billing Licenses section. | In Progress
Company -> Users | When added a user from Super Admin and logs in this created user, only the Home, Phone, and Admin sections are visible after login. | In Progress
Rate Card -> Rate Card Details | Pagination page-size selector UI issue: When clicking on the page-size dropdown, the dropdown values appear behind the table and are not visible. | pass | Dropdown is showing but Its not working. Filter Pagination issue.mp4
UCaaS Super-Admin - DID numbers https://admin-ucaas.mycountrymobile.com/ | If the Super-Admn deletes a user's DID number, it does not get deleted from the user account, and still the user is able to use that DID number. | pass | The number is deleted, but if it is assigned to a user, it is not removed from the user, and the user can continue using it until the number is changed.
The Company->admin Login | The Super admin is not able login with the given company's admin login option | pass | Umar/Fixed
Company dashboard | The yearly meeting graph is not showing any report, even though the company had their meeting history. | pass | Umar/Not Fixed and also the graph name has been changed. It was “Yearly Meeting summary” but it has been changed to “Yearly Company summary.”
User's own DID Number | DID number- the super admin shall have the option to add the user's own DID number, which can be assigned later by the admin | DONE and need to discuss
Home Dashboard | Need to rename the 'new company' as 'active company', which is not appearing on the superadmin home dashboard. | pass | Fixed on QA
Companies-> Profile | When the company name is updated, the changes are not reflected in the customer portal, but still it is updated correctly in the Super Admin panel, also the company name is editable with the same name as per the other company. | ADD VIDEO | Video Added
Companies->Dashboard | The company dashboard graphs are inaccurate and displaying incorrect information. | pass | Fixed on QA
Companies-> Profile | In the Company Info section, the total number of members and the number of DIDs purchased are not shown properly which seems incorrect. | pass | Not Fixed properly, need to discuss this
Companies->Calls->Filter | In Companies > Calls > Filter > Select Type, “Missed Calls” and “Voicemail” are not visible and are incorrectly listed under “Inbound Calls.” | Done | Umar/Not Fixed
Video Meetings | In the Duration column, incorrect durations are shown for all meetings (01:00 for instant meetings and 00:15 for scheduled meetings) | Format fixed on qa | Not Fixed
Companies->Virtual Number ->Search Bar | search bar is not working in Virtual Number section. | FIXED - Added search on number , name and assingTo name | Anusha-Not Fixed
SMS-> search | The ‘Select Date’ dropdown is not working and shows the error message ‘Something went wrong.’ | pass | Fixed on QA
SMS-> search | Search bar is not working. | pass | Umar/Not Fixed search result is showing but in this number is not showing.
DID Number-> assigned DID | In the search bar, searching by number is not working and no results are shown.
DID Number-> Unassigned DID | In Unassigned DID section the any Unassigned DID number not showing.
Companies->Virtual Number ->Filter | In the Companies -> Virtual Numbers section, the “Select DID Type” filter currently shows only two options: Local and Toll-Free. The Mobile type option is missing, and the search bar in the Select Type dropdown is not required and should be removed. | pass | Umar/Fixed
Scheduled Meeting and event | When any company user schedules or creates an event, the scheduled meeting or event appears in the Video Meeting section of all companies. | pass | Umar/Fixed
Companies->Video Meetings | In the Upcoming Meetings section, the “Select Type” and “Select Status” dropdowns include a search bar, which is not required and should be removed. | pass | Umar/Fixed
UCaaS Super-Admin https://admin-ucaas.mycountrymobile.com/ | In the Super-Admin UI, the admin is not able to make a user's account deactivate or expire, upon using on these functions, those user will be logged out only. and after logging in again, it will fetch some errors, but can still work with their account. | pass | Umar/Fixed
Video Meetings | In Video Meeting → Search Filter, when selecting the Scheduled type, no results are displayed even though meetings exist. | pass | Umar/Fixed
Companies->Video Meetings | In Video Meetings, the label “Attendees” should be changed to “Invitees.” | pass | Umar/Fixed
Companies->Video Meetings | In the Past Meetings section, when filtering by status “Complete,” an error popup appears saying “Something went wrong.” | pass | Umar/Fixed
Companies | When Search any company in the search result the company plan name is not showing. | pass | Umar/Fixed
Companies->Calls->Filter | In Companies > Calls > Filter > Select Date, when selecting “Last 7 Days,” records from 8 days are being displayed. | fixed on qa
Companies->Calls->Filter | In Companies > Calls > Filter, the “Enter Name” search is not working. | pass | Umar/Fixed